## Table 1 UHVDC projects in the p
Name | Capacity | Time period | Note
Trạm chuyển đổi AC/DC/AC (Back-To- Back) 500kV Lào Cai | 3000 MW | 2026-2030 | Serving the connection of electricity import from China, implemented when the competent authority approves the policy of importing electricity from China via Lao Cai, if the Back-to-Back conversion station is built in Vietnam territory.
Đường dây một chiều Bipole HVDC từ Trung Trung Bộ 1 - Bắc Bộ 1 | 2x700km | 2031-2035 | The length, cross-section of conductors and the route of the line will be determined precisely during the project implementation phase in case of high power development in the Vung Ang, Quang Dinh and Quang Tri areas. Consider the option of utilizing the old 500kV Quang Tri - Vung Ang - Nho Quan line route.
Trạm converter Trung Trung Bộ 1 | 5000- 10000 MW | 2031-2035 | The scale and location of the station will be determined during the project implementation phase. Consideration is given to placing it in Quang Binh and Quang Tri areas.
Trạm converter Bắc Bộ 1 | 5000- 10000 MW | 2031-2035 | The scale and location of the station will be determined during the project implementation phase. Consideration is given to locations in Ha Nam, Nam Dinh, Thai Binh, Hai Duong, and Bac Giang provinces.
Đường dây một chiều Bipole HVDC từ Trung Trung Bộ 2 - Bắc Bộ 2 | 2x1050km | 2031-2035 | The length, cross-section of conductors and line direction will be determined precisely during the project implementation phase.
Trạm converter Trung Trung Bộ 2 | 5000- 10000 MW | 2031-2035 | The scale and location of the station will be determined during the project implementation phase. Consideration is given to locating in Quang Ngai area.
Trạm converter Bắc Bộ 2 | 5000- 10000 MW | 2031-2035 | The scale and location of the station will be determined during the project implementation phase. Consideration is given to placing it in the western districts of Hanoi.
Đường dây một chiều Bipole HVDC từ Nam Trung Bộ - Bắc Bộ 3 | 2x1550km | 2031-2035 | The length, cross-section of conductors and the direction of the line will be determined precisely during the project implementation phase. Contingency for further development of the South Central Power Source.
Trạm converter Nam Trung Bộ | 4000- 10000 MW | 2031-2035 | The scale and location of the station will be determined during the project implementation phase. Consideration is given to placing it in Ninh Thuan province.
Trạm converter Bắc Bộ 3 | 4000- 10000 MW | 2031-2035 | The scale and location of the station will be determined during the project implementation phase. Consideration is given to locating in Hung Yen province.
Đường dây từ Bà Rịa - Vũng Tàu ra Hải Phòng | 2x1700km | 2031-2035 | The length, cross-section of conductors and line direction will be determined precisely during the project implementation phase in case of high power development in the Southern region.

## Table 2 Orientation of UHVAC 76
Name | Capacity | Time | Note
Đường dây 765÷1000 kV Nam Trung Bộ 1 - Nam Bộ 1 | 600km | 2031-2035 | In case the South Central power source development is higher than expected, consider the option of releasing nuclear power capacity and increasing the transmission capacity connecting South Central - South by using the 765÷1000 kV ultra-high voltage AC grid instead of the 500 kV transmission option. The scale, progress and direction of the transmission line will be determined precisely during the project implementation phase.
Đường dây 765÷1000 kV Nam Trung Bộ 2 - Nam Bộ 2 | 600km | 2031-2035 | In case the South Central power source development is higher than expected, consider the option of releasing nuclear power capacity and increasing the transmission capacity connecting South Central - South by using the 765÷1000 kV ultra-high voltage AC grid instead of the 500 kV transmission option. The scale, progress and direction of the transmission line will be determined precisely during the project implementation phase.
TBA 765÷1000 kV Nam Trung Bộ 1 | 4000 MVA | 2031-2035 | New construction, in case of high development of South Central power source, synchronize the 765÷1000 kV South Central 1 - South 1 transmission line. Progress, scale and station location will be determined precisely during the project implementation phase.
TBA 765÷1000 kV Nam Trung Bộ 2 | 4000 MVA | 2031-2035 | New construction, in case of high development of South Central power source, synchronize the 765÷1000 kV South Central 2 - South 2 transmission line. Progress, scale and station location will be determined precisely during the project implementation phase.
TBA 765÷1000 kV Nam Bộ 1 | 4000 MVA | 2031-2035 | New construction, in case of high development of South Central power source, synchronize the 765÷1000 kV South Central 1 - South 1 transmission line. Progress, scale and station location will be determined precisely during the project implementation phase.
TBA 765÷1000 kV Nam Bộ 2 | 4000 MVA | 2031-2035 | New construction, in case of high development of South Central power source, synchronize the 765+1000 kV South Central 2 - South 2 transmission line. Progress, scale and station location will be determined precisely during the project implementation phase.

## TABLE 3 transformer stations no
Name | Capactiy (MVA) | Time | Note
Tây Hà Nội | 1800 | 2025-2030 | Renovation and capacity improvement
Sơn Tây | 1800 | 2025-2030 | New construction
Nam Hà Nội | 1800 | 2025-2030 | New construction
Đan Phượng | 1800 | 2025-2030 | New construction, consideration of connection to Dan Phuong 220kV station
Hải Phòng | 1800 | 2025-2030 | New construction
Hải Phòng 2 | 1800 | 2025-2030 | New construction
BB 1 (*) | 2700 | 2025-2030 | New construction, synchronized power source
Gia Lộc | 900 | 2025-2030 | New construction
Phố Nối | 1800 | 2025-2030 | Renovation and capacity improvement
Hưng Yên 1 | 1800 | 2025-2030 | New construction, renaming from 500 kV Long Bien substation in Power Plan VIII
Hưng Yên 2 | 900 | 2025-2030 | New construction
Nam Định | 1800 | 2025-2030 | New construction, the names in the list of 500kV, 220kV lines are Nam Dinh Thermal Power Plant, Nam Dinh 1 Thermal Power Plant
Thái Bình | 1200 | 2025-2030 | New construction
Trạm cắt Hòa Bình 2 | Switching station | 2025-2030 | Build new storage station
Lào Cai | 2700 | 2025-2030 | New construction
Lạng Sơn | 1800 | 2025-2030 | New construction
Yên Bái (*) | 1800 | 2025-2030 | New construction
Thái Nguyên | 1800 | 2025-2030 | New construction
Việt Trì | 1800 | 2025-2030 | Renovation and capacity improvement
Vĩnh Yên | 1800 | 2025-2030 | New construction
Bắc Giang | 900 | 2025-2030 | New construction
Yên Thế | 900 | 2025-2030 | New construction
Bắc Ninh | 1800 | 2025-2030 | New construction
Bắc Ninh 2 | 1800 | 2025-2030 | New construction
Quảng Ninh | 1800 | 2025-2030 | New construction
Lai Châu | 1800 | 2025-2030 | Renovation and capacity improvement
Than Uyên | 2700 | 2025-2030 | New construction
Điện Biên | 2700 | 2025-2030 | New construction
Sơn La 1 (*) | 1800 | 2025-2030 | New construction
Sơn La 2 (*) | 1800 | 2025-2030 | New construction
Hòa Bình | 1800 | 2025-2030 | Renovation and capacity improvement
Nghi Sơn | 1800 | 2025-2030 | Renovation and capacity improvement
Thanh Hóa | 1800 | 2025-2030 | Renovation and capacity improvement
Nam Cấm |  | 2025-2030 | Build new switching station to serve electricity import connection from Laos
Quỳnh Lưu | 1800 | 2025-2030 | New construction
Hà Tĩnh 2 | 2700 | 2025-2030 | New construction
Dự phòng phát sinh TBA xây mới, cải tạo nâng công suất | 4500 | 2025-2030 | New construction and renovation, capacity expansion
Thường Tín | 2700 | 2031-2035 | Renovation and capacity improvement
Đông Anh | 2700 | 2031-2035 | Renovation and capacity improvement
Tây Hà Nội | 2700 | 2031-2035 | Renovation and capacity improvement
Nam Hà Nội | 2700 | 2031-2035 | Renovation and capacity improvement
Đan Phượng | 2700 | 2031-2035 | Renovation and capacity improvement
Vân Trì | 1800 | 2031-2035 | New Construction
Hải Phòng 2 | 2700 | 2031-2035 | Renovation and Capacity improvement
BB 1 (*) | 3600 | 2031-2035 | Renovation and capacity improvement
BB 2 (*) | 3600 | 2031-2035 | New construction, synchronized power source
Gia Lộc | 1800 | 2031-2035 | Renovation and capacity improvement
Hưng Yên 1 | 2700 | 2031-2035 | Renovation and capacity improvement
Hưng Yên 2 | 1800 | 2031-2035 | Renovation and capacity improvement
Hà Nam | 1800 | 2031-2035 | New construction
Nam Định | 2700 | 2031-2035 | Renovation, capacity increase, names in the list of 500kV, 220kV lines are Nam Dinh Thermal Power Plant, Nam Dinh 1 Thermal Power Plant
Nam Định 2 | 900 | 2031-2035 | New construction
Nam Định 3 | 1800 | 2031-2035 | New construction, synchronized with the load of Ninh Co EZ (according to the proposal of Nam Dinh Provincial People's Committee in Document No. 06/UBND-VP5 dated January 3, 2025) and in case of developing specialized load when 220 kV substation cannot ensure power supply. Consider scale up to 3,600 MVA when load demand develops strongly; consider connecting self-produced and self-consumed renewable energy and LNG sources to supply power to this load.
Thái Bình | 1800 | 2031-2035 | Renovation and capacity improvement
BB 4 (*) | 2700 | 2031-2035 | New construction, synchronized power source
Lạng Sơn 2 (*) | 1800 | 2031-2035 | New Construction
Hà Giang | 1800 | 2031-2035 | New construction
Thái Nguyên 2 | 900 | 2031-2035 | New construction
Phú Thọ | 1800 | 2031-2035 | New construction
Vĩnh Tường | 1800 | 2031-2035 | New construction
Bắc Giang | 1800 | 2031-2035 | Renovation and capacity improvement
Yên Thế | 1800 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh | 2700 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh 2 | 2700 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh 3 | 1800 | 2031-2035 | New Construction
BB 3 (*) | 2700 | 2031-2035 | New construction, synchronized power source
Hải Hà | 900 | 2031-2035 | New construction
Quảng Ninh 2 | 1800 | 2031-2035 | Renovation and capacity improvement
NLTT Lai Châu 1 (*) | 1800 | 2031-2035 | New construction
Sơn La | 2700 | 2031-2035 | Renovation and capacity improvement
Thanh Hóa | 2700 | 2031-2035 | Renovation and capacity improvement
Tĩnh Gia | 1800 | 2031-2035 | New Construction
Nam Cấm | 900 | 2031-2035 | Install additional transformers at the switching station to supply power to local loads (if necessary), consider connecting to the 220kV Nam Cam station (if necessary)
Hà Tĩnh | 1800 | 2031-2035 | Renovation and capacity improvement
Dự phòng phát sinh TBA xây mới, cải tạo nâng công suất | 2700 | 2031-2035 | New construction and renovation, capacity expansion

## Table 4 500 kV lines in the Nor
Name | No. of circuits × km | Time | Notes
Mạch 2 Nho Quan - Thường Tín | 1x75 | 2025-2030 | Convert one circuit into two circuits
Đan Phượng - Rẽ Tây Hà Nội - Vĩnh Yên | 4x5 | 2025-2030 | Connection to 500 kV Dan Phuong Substation
Hưng Yên 1 - Rẽ Phố Nối - Thường Tín | 2x8 | 2025-2030 | Connecting 500 kV Hung Yen 1 substation, replacing the 500 kV Long Bien - Pho Noi - Thuong Tin line in Power Planning VIII
Hưng Yên 2 - Hưng Yên 1 | 2x35 | 2025-2030 | Connection of 500kV Hung Yen 2 Substation
Nam Hà Nội - Rẽ Nho Quan - Thường Tín | 4x5 | 2025-2030 | Connection to 500 kV South Hanoi Substation
Sơn Tây - Đan Phượng | 2x20 | 2025-2030 | Connection to 500 kV Son Tay Substation
Tây Hà Nội - Vĩnh Yên | 2x70 | 2025-2030 | New construction
BB 1 - Hải Phòng (*) | 2x25 | 2025-2030 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Hải Phòng - Thái Bình | 2x38 | 2025-2030 | Connection to 500 kV Hai Phong Substation
Quảng Ninh 2 - Rẽ Quảng Ninh - Phố Nối và NĐ Thăng Long - Phố Nối | 4x5 | 2025-2030 | New construction
Hải Phòng - Hải Phòng 2 | 2x20 | 2025-2030 | New construction
BB1 - Quảng Ninh 2 (*) | 2x60 | 2025-2030 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Gia Lộc - Rẽ Thái Bình - Phố Nối | 4x13 | 2025-2030 | Gia Loc 500 kV Substation Connection
Thái Bình - Rẽ NMNĐ Nam Định 1 - Phố Nối | 4x1 | 2025-2030 | Connection to 500 kV Thai Binh Substation
Nam Định - Rẽ Thanh Hóa - Phố Nối | 4x1 | 2025-2030 | New construction, connection, completion of Nam Dinh 500kV substation diagram.
Sam Nuea - Trạm cắt Hòa Bình 2 | 2x110 | 2025-2030 | New construction
Trạm cắt Hòa Bình 2 - Rẽ Hòa Bình - Nho Quan và Sơn La - Nho Quan | 4x5 | 2025-2030 | New construction
Trạm cắt Hòa Bình 2 - Tây Hà Nội | 2x80 | 2025-2030 | New construction
Biên giới Việt Nam - Trung Quốc - Lào Cai | 2x65 | 2025-2030 | Buy electricity from China
Lào Cai - Vĩnh Yên | 2x210 | 2025-2030 | Connecting 500 kV Lao Cai substation, clearing small hydropower plants and making provision to buy electricity from China
Lạng Sơn - Bắc Giang (*) | 2x120 | 2025-2030 | New construction
Lạng Sơn - Yên Thế (*) | 2x120 | 2025-2030 | New construction
Yên Bái - Thái Nguyên (*) | 2x100 | 2025-2030 | New construction, in case of high development of renewable energy sources in the Northwest, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025.
Yên Bái - Rẽ Lào Cai - Vĩnh Yên (*) | 4x20 | 2025-2030 | New construction, in case of high development of renewable energy sources in the Northwest, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025.
Hiệp Hòa - Thái Nguyên | 2x29 | 2025-2030 | Connection to 500 kV Thai Nguyen Substation
Yên Thế - Thái Nguyên | 2x70 | 2025-2030 | New construction
Vĩnh Yên - Rẽ Sơn La - Hiệp Hòa và Việt Trì - Hiệp Hòa | 4x5 | 2025-2030 | Connection to 500 kV Vinh Yen Substation
Bắc Giang - Bắc Ninh | 2x40 | 2025-2030 | New construction
Bắc Giang - Rẽ Quảng Ninh - Hiệp Hòa | 4x5 | 2025-2030 | Connection to 500 kV Bac Giang Substation
Bắc Ninh - Rẽ Đông Anh - Phố Nối | 2x1 | 2025-2030 | Connection to 500 kV Bac Ninh Substation
Bắc Ninh 2 - Rẽ Bắc Giang - Hiệp Hòa | 4x10 | 2025-2030 | Connection of 500 kV Bac Ninh 2 substation
LNG Quảng Ninh - Quảng Ninh | 2x30 | 2025-2030 | New construction, synchronized power source. Replace the 500 kV LNG Quang Ninh 1 - Quang Ninh line in Power Plan VIII. In case the 500 kV Quang Ninh substation cannot expand the feeder, carry out a transition connection to the 500 kV Quang Ninh - Hiep Hoa line.
Lai Châu - Than Uyên | 2x75 | 2025-2030 | New construction
Than Uyên - Yên Bái (*) | 2x170 | 2025-2030 | New construction, in case of high development of renewable energy sources in the Northwest, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025.
Điện Biên - Lai Châu (*) | 2x50 | 2025-2030 | New construction
Sơn La 1 - Rẽ Sơn La - Hòa Bình và Sơn La - Nho Quan (*) | 2x150 | 2025-2030 | New construction, in case of high development of renewable energy sources in the Northwest, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025.
Sơn La 1 - Sơn Tây (*) | 2x150 | 2025-2030 | New construction, in case of high development of renewable energy sources in the Northwest, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025.
Sơn La 2 - Sơn La 1 (*) | 2x50 | 2025-2030 | New construction, in case of high development of renewable energy sources in the Northwest, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025.
TĐ Hòa Bình mở rộng - Rẽ Hòa Bình - Nho Quan | 2x1 | 2025-2030 | Synchronized with Hoa Binh MR.
Quỳnh Lưu - Rẽ Quảng Trạch - Thanh Hóa | 4x5 | 2025-2030 | New construction
LNG Nghi Sơn - LNG Quỳnh Lập | 2x10 | 2025-2030 | New construction, in case of LNG Nghi Son, LNG Quynh Lap is behind schedule, invest first in Quynh Luu - Hung Yen 1 line
LNG Nghi Sơn - Hưng Yên 2 | 2x190 | 2025-2030 | New construction, in case of LNG Nghi Son, LNG Quynh Lap is behind schedule, invest first in Quynh Luu - Hung Yen 2 line
LNG Quỳnh Lập - Quỳnh Lưu | 2x15 | 2025-2030 | New construction, in case of LNG Nghi Son, LNG Quynh Lap is behind schedule, invest first in Quynh Luu - Hung Yen 2 line
Đấu nối TĐTN Bắc Trung Bộ | 2x50 | 2025-2030 | New construction, source synchronization
LNG Quảng Trạch II - Quảng Trạch | 2x1 | 2025-2030 | New construction, synchronized power source
Trạm cắt Nam Cấm - Rẽ Vũng Áng - Nho Quan | 4x12 | 2025-2030 | New construction, serving the connection of imported power source to Laos. Transition on 02 existing 500 kV Vung Ang - Nho Quan line circuits (circuits 1,2)
Vũng Áng - Trạm cắt Hòa Bình 2 | 2x380 | 2025-2030 | New construction, using large cross-section phase wires, switching the connection of the 500kV Vung Ang - Da Nang - Ha Tinh line (circuits 3,4), combined with replacing the superheat wire in this section.
Vũng Áng - Rẽ Hà Tĩnh - Đà Nẵng (mạch 3,4) | 2x16 | 2025-2030 | Transition to 500 kV Ha Tinh - Da Nang line circuit 2
Hà Tĩnh 2 - Rẽ Vũng Áng - Hà Tĩnh (*) | 4x5 | 2025-2030 | New construction
ĐG Phila - Trạm cất 500 kV Nam Cấm | 2x35 | 2025-2030 | Proposed plan in the document of the Provincial People's Committee, serving the import of Lao electronics
ĐG Cha Lo - TBA 500 kV Hà Tĩnh | 2x50 | 2025-2030 | Proposed plan in the document of the Provincial People's Committee, serving the import of electricity from Laos
Đấu nối Trạm chuyển đổi AC/DC/AC (Back-To-Back) 500kV Lào Cai | 4x2 | 2025-2030 | Serving the connection of electricity import from China, implemented when the competent authority approves the policy of importing electricity from China via Lao Cai, if the Back-to-Back conversion station is built in Vietnam territory.
Dự phòng dấu nối các nguồn điện tại các tỉnh Boulikhamxay, Khammouane, Lào | 600 | 2025-2030 | New construction
Dự phòng phát sinh đường dây 500 kV cải tạo và xây mới | 200 | 2025-2030 | New construction and renovation
Đấu nối trạm converter HVDC Bắc Bộ 1 (*) | 120 | 2031-2035 | New construction, length, cross-section of conductors and line direction will be determined precisely during the project implementation phase.
Đấu nối trạm converter HVDC Bắc Bộ 2 (*) | 120 | 2031-2035 | New construction, length, cross-section of conductors and line direction will be determined precisely during the project implementation phase.
Đấu nối trạm converter HVDC Bắc Bộ 3 (*) | 120 | 2031-2035 | New construction, length, cross-section of conductors and line direction will be determined precisely during the project implementation phase.
Vân Trì - Vĩnh Yên | 2x40 | 2031-2035 | New construction
BB 2 - Rẽ BB 1 - Hải Phòng 2 (*) | 4x5 | 2031-2035 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Hà Nam - Thái Bình | 2x20 | 2031-2035 | New construction
Nam Định 2 - Rẽ LNG Nghi Sơn - Hưng Yên 2 | 4x5 | 2031-2035 | New construction
Nam Định - Nam Định 3 | 2x18 | 2031-2035 | New construction, synchronized with 500 kV Nam Dinh 3 substation
BB 4 - Bắc Giang (*) | 2x135 | 2031-2035 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Hà Giang - Rẽ Yên Bái - Thái Nguyên | 2x180 | 2031-2035 | New construction
Lạng Sơn 2 500 kV - Rẽ Lạng Sơn - Yên Thế | 4x10 | 2031-2035 | New construction
Thái Nguyên 2 - Thái Nguyên - Yên Thế | 2x20 | 2031-2035 | New construction
Phú Thọ - Rẽ Sơn La - Việt Trì | 4x20 | 2031-2035 | New construction
Sơn Tây - Vĩnh Tường | 2x20 | 2031-2035 | New construction
Bắc Ninh 3 - Rẽ Hưng Yên 1 - Phố Nối | 4x10 | 2031-2035 | New construction
BB 3 - Lạng Sơn (*) | 2x140 | 2031-2035 | New construction, synchronized with the scale and progress of the offshore wind power source in Bac Bo. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Hải Hà - Rẽ BB 3 - Lạng Sơn | 2x5 | 2031-2035 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
NLTT Lai Châu 1 - Rẽ Lai Châu - Than Uyên (*) | 4x20 | 2031-2035 | New construction
LNG Công Thanh - Rẽ Nghi Sơn - Nho Quan | 2x20 | 2031-2035 | New construction, synchronized power source. Specific connection plan is accurate during project implementation phase.
LNG Thái Bình GĐ 2 - Thái Bình | 2x50 | 2031-2035 | New construction, synchronized power source. Specific connection plan is accurate during project implementation phase.
LNG Vũng Áng III - Rẽ Vũng Áng - Quảng Trạch | 2x20 | 2031-2035 | New construction, synchronized power source. Specific connection plan is accurate during project implementation phase.
LNG Thanh Hóa - LNG Công Thanh | 2x5 | 2031-2035 | New construction, synchronized power source. Specific connection plan is accurate during project implementation phase.
LNG Công Thanh - Bắc Ninh 3 | 2x220 | 2031-2035 | New construction, synchronized power source. Specific connection plan is accurate in project implementation phase. Consider using four-circuit poles, maximizing route direction with LNG Nghi Son - Hung Yen 1.
Đấu nối TĐTN Bắc Bộ 1 (*) | 4x20 | 2031-2035 | New construction, synchronized power source
TĐTN Đông Phù Yên - Rẽ Sơn La - Việt Trì và Sơn La - Vĩnh Yên | 4x20 | 2031-2035 | New construction, synchronized power source
TĐTN Bắc Bộ 1 - rẽ Sơn La 1 - Sơn Tây (*) | 4x20 | 2031-2035 | New construction, synchronized power source
Tĩnh Gia - Rẽ LNG Nghi Sơn - Hưng Yên 2 | 4x4 | 2031-2035 | New construction
LNG Hải Phòng - TBA 500 kV Hải Phòng (hoặc TBA 500 kV Gia Lộc) | 2x45 | 2031-2035 | Synchronizing Hai Phong LNG Power Plant Phase I
LNG Quảng Trạch III - Quảng Trạch | 2x1 | 2031-2035 | New construction, synchronized power source
Cải tạo Quảng Trị - Vũng Áng (mạch 2) | 2x200 | 2031-2035 | New construction, contingency plan in case of deploying HVDC Central Central 1 - North 1, utilizing the existing 500 kV Quang Tri - Vung Ang line
TĐ Sơn La M R - TĐ Sơn La - Lai Châu | 1x5 | 2031-2035 | New construction, synchronized power source. Proposed plan in EVN's Official Dispatch No. 862/EVN-KH dated February 11, 2025. Specific connection plan is accurate during project implementation phase.
TĐ Lai Châu MR - Rẽ TĐ Lai Châu - Lai Châu | 2x1 | 2031-2035 | New construction, synchronized power source. Proposed plan in EVN Document No. 862/EVN-KH dated February 11, 2025. Specific connection plan is accurate during project implementation phase.
Cải tạo Vũng Áng - Nho Quan (mạch 1) | 2x360 | 2031-2035 | Renovation of existing 500 kV line into 02 circuits
Dự phòng phát sinh đường dây 500 kV cải tạo và xây mới |  | 340

## Table 5 built and renovated 220
Name | Capacity (MVA) | Time | Note
Vân Trì | 750 | 2025-2030 | Renovation and capacity improvement
Tây Hà Nội | 750 | 2025-2030 | Renovation and capacity improvement
Sóc Sơn 2 | 250 | 2025-2030 | New construction
Văn Điển | 500 | 2025-2030 | New construction
Long Biên 2 | 500 | 2025-2030 | New construction
Mê Linh | 500 | 2025-2030 | New construction
Chương Mỹ | 250 | 2025-2030 | New construction
Ứng Hòa | 500 | 2025-2030 | New construction
Đại Mỗ | 750 | 2025-2030 | New construction
Hòa Lạc | 500 | 2025-2030 | New construction
Cầu Giấy | 250 | 2025-2030 | New construction
Hai Bà Trưng | 250 | 2025-2030 | New construction
Thanh Xuân | 750 | 2025-2030 | New construction
Đan Phượng | 500 | 2025-2030 | New construction
Phú Xuyên | 250 | 2025-2030 | New construction
Hòa Lạc 2 | 500 | 2025-2030 | New construction
NLTT Hà Nội 2 (*) | 500 | 2025-2030 | New construction
Vật Cách | 500 | 2025-2030 | Renovation and capacity improvement
NĐ Hải Phòng | 500 | 2025-2030 | Renovation and capacity improvement
Đồ Sơn | 250 | 2025-2030 | New construction
An Lão | 500 | 2025-2030 | New construction
Đại Bản | 250 | 2025-2030 | New construction
Dương Kinh | 500 | 2025-2030 | New construction
Tiên Lãng | 500 | 2025-2030 | New construction
Cát Hải | 500 | 2025-2030 | New construction
NĐ Phả Lại | 750 | 2025-2030 | Renovation and capacity improvement
Gia Lộc | 500 | 2025-2030 | New construction
Tứ Kỳ | 250 | 2025-2030 | New construction
NĐ Hải Dương | 500 | 2025-2030 | Renovation and capacity improvement
Tân Việt | 500 | 2025-2030 | New construction
Thanh Hà | 250 | 2025-2030 | New construction
Nhị Chiểu | 250 | 2025-2030 | New construction
Nam Sách | 250 | 2025-2030 | New construction
Thanh Miện | 250 | 2025-2030 | New construction
Hưng Yên 2 500 kV nối cấp | 250 | 2025-2030 | New construction
Bãi Sậy | 500 | 2025-2030 | New construction
Văn Giang | 250 | 2025-2030 | New construction
Lý Nhân | 500 | 2025-2030 | New construction
Đồng Văn | 750 | 2025-2030 | New construction
Hải Hậu | 500 | 2025-2030 | New construction
Nam Định 2 | 250 | 2025-2030 | New construction
Nghĩa Hưng | 500 | 2025-2030 | New construction
Nam Định 3 | 750 | 2025-2030 | New construction
Giao Thủy | 250 | 2025-2030 | New construction
Quỳnh Phụ | 500 | 2025-2030 | New construction
Vũ Thư | 500 | 2025-2030 | New construction
Thái Bình 500 kV nối cấp | 500 | 2025-2030 | New construction
Ninh Bình 2 | 500 | 2025-2030 | New construction
Nho Quan 500 kV nối cấp | 500 | 2025-2030 | Renovation and capacity improvement
Tam Điệp | 250 | 2025-2030 | New construction
Gia Viễn | 500 | 2025-2030 | New construction, implemented in case of relocation of Ninh Binh 220kV substation
Hà Giang | 375 | 2025-2030 | Renovation and capacity improvement
Bắc Quang | 500 | 2025-2030 | Renovation and capacity improvement
Cao Bằng | 500 | 2025-2030 | Renovation and capacity improvement
Bắc Hà | 250 | 2025-2030 | New construction
Bát Xát | 500 | 2025-2030 | New construction
Lào Cai 500 kV nối cấp | 500 | 2025-2030 | New construction
Văn Bàn | 250 | 2025-2030 | New construction
Bắc Kạn 1 (*) | 500 | 2025-2030 | New construction
Lạng Sơn | 500 | 2025-2030 | Renovation and capacity improvement
Đồng Mỏ | 500 | 2025-2030 | New construction
Lạng Sơn 2 (*) | 500 | 2025-2030 | New construction
Lạng Sơn 1 (*) | 500 | 2025-2030 | New construction
Tuyên Quang | 500 | 2025-2030 | Renovation and capacity improvement
Nghĩa Lộ | 500 | 2025-2030 | New construction
Yên Bái | 500 | 2025-2030 | Renovation and capacity improvement
Lục Yên | 250 | 2025-2030 | New construction
Yên Bái 1 (*) | 500 | 2025-2030 | New construction
Yên Bái 2 (*) | 500 | 2025-2030 | New construction
Sông Công | 500 | 2025-2030 | New construction
Phú Bình 2 | 500 | 2025-2030 | New construction
Đại Từ | 250 | 2025-2030 | New construction
NLTT Thái Nguyên 2 (*) | 500 | 2025-2030 | New construction
Phú Thọ 2 | 500 | 2025-2030 | New construction
Việt Trì 500 kV nối cấp | 500 | 2025-2030 | New construction
Phú Thọ 3 | 250 | 2025-2030 | New construction
Tam Dương | 500 | 2025-2030 | New construction
Bá Thiện | 500 | 2025-2030 | New construction
Phúc Yên | 250 | 2025-2030 | New construction
Chấn Hưng | 250 | 2025-2030 | New construction
Bắc Giang 500 kV nối cấp | 500 | 2025-2030 | New construction
Lạng Giang | 250 | 2025-2030 | New construction
Yên Dũng | 500 | 2025-2030 | New construction
Hiệp Hòa 2 | 500 | 2025-2030 | New construction
Tân Yên | 500 | 2025-2030 | New construction
Việt Yên | 500 | 2025-2030 | New construction
Bắc Giang 1 (*) | 500 | 2025-2030 | New construction
Bắc Ninh 6 | 500 | 2025-2030 | New construction
Bắc Ninh 4 | 500 | 2025-2030 | New construction
Bắc Ninh 5 | 500 | 2025-2030 | New construction
Bắc Ninh 7 | 500 | 2025-2030 | New construction
Bắc Ninh 500 kV nối cấp | 500 | 2025-2030 | New construction
Hoành Bồ | 500 | 2025-2030 | Renovation and capacity improvement
Cẩm Phả | 500 | 2025-2030 | Renovation and capacity improvement
Quảng Ninh 500 kV nối cấp | 500 | 2025-2030 | Renovation and capacity improvement
Khe Thần | 126 | 2025-2030 | New construction
Móng Cái | 500 | 2025-2030 | New construction
Yên Hưng | 750 | 2025-2030 | Renovation and capacity improvement
Hải Hà 2 | 250 | 2025-2030 | New construction to replace 220 kV substation in Hai Ha Industrial Park
Cộng Hòa | 500 | 2025-2030 | New construction
Nam Hòa | 500 | 2025-2030 | New construction
Quảng Ninh 1 (*) | 500 | 2025-2030 | New construction
NLTT Quảng Ninh 2 (*) | 500 | 2025-2030 | New construction
Mường Tè | 750 | 2025-2030 | Renovation and capacity improvement
Pắc Ma | 500 | 2025-2030 | New construction
Phong Thổ | 500 | 2025-2030 | New construction
Sìn Hồ | 250 | 2025-2030 | New construction
Than Uyên | 750 | 2025-2030 | Renovation and capacity improvement
NLTT Lai Châu 1 (*) | 500 | 2025-2030 | New construction
NLTT Lai Châu 2 (*) | 500 | 2025-2030 | New construction
Điện Biên | 500 | 2025-2030 | New construction
Điện Biên 1 (*) | 500 | 2025-2030 | New construction
Điện Biên 2 (*) | 500 | 2025-2030 | New construction
Mường La | 500 | 2025-2030 | Renovation and capacity improvement
Sông Mã | 250 | 2025-2030 | New construction
Mộc Châu | 250 | 2025-2030 | New construction
Phù Yên | 375 | 2025-2030 | New construction
Sơn La 1 (*) | 250 | 2025-2030 | New construction
Sơn La 2 (*) | 500 | 2025-2030 | New construction
Sơn La 3 (*) | 500 | 2025-2030 | New construction
Sơn La 4 (*) | 500 | 2025-2030 | New construction
Sơn La 5 (*) | 500 | 2025-2030 | New construction
Sơn La 6 (*) | 500 | 2025-2030 | New construction
Hòa Bình | 500 | 2025-2030 | Renovation and capacity improvement
Yên Thủy | 250 | 2025-2030 | Renovation and capacity improvement
Tân Lạc | 250 | 2025-2030 | New construction
Sầm Sơn | 500 | 2025-2030 | New construction
Tĩnh Gia | 500 | 2025-2030 | New construction
KKT Nghi Sơn | 750 | 2025-2030 | Renovation and capacity improvement
Lọc hoá dầu Nghi Sơn | 500 | 2025-2030 | New construction
Hậu Lộc | 500 | 2025-2030 | New construction
Thiệu Hóa | 250 | 2025-2030 | New construction
Thiệu Yên | 250 | 2025-2030 | New construction
Thanh Hóa 1 (*) | 500 | 2025-2030 | New construction
Đồng Vàng | 500 | 2025-2030 | New construction
Nghi Sơn 2 | 500 | 2025-2030 | New construction
Đô Lương | 500 | 2025-2030 | Renovation and capacity improvement
Nam Cấm | 500 | 2025-2030 | New construction
Quỳ Hợp | 250 | 2025-2030 | New construction
Tương Dương | 250 | 2025-2030 | Renovation and capacity improvement
Bá Thước | 250 | 2025-2030 | New construction
Hoàng Mai | 500 | 2025-2030 | New construction
Hoàng Mai 2 | 250 | 2025-2030 | New construction
Quỳnh Lưu 500kV nối cấp | 500 | 2025-2030 | New construction
NLTT Nghệ An 1 (*) | 500 | 2025-2030 | New construction
NLTT Nghệ An 2 (*) | 500 | 2025-2030 | New construction
Hà Tĩnh | 500 | 2025-2030 | Renovation and capacity improvement
Can Lộc | 250 | 2025-2030 | New construction
Vũng Áng | 500 | 2025-2030 | New construction
Vũng Áng 2 | 500 | 2025-2030 | New construction
Hà Tĩnh 1 (*) | 500 | 2025-2030 | New construction
NLTT Hà Tĩnh 2 (*) | 500 | 2025-2030 | New construction
NLTT Hà Tĩnh 3 (*) | 500 | 2025-2030 | New construction
NLTT Hà Tĩnh 4 (*) | 500 | 2025-2030 | New construction
NLTT Hà Tĩnh 5 (*) | 500 | 2025-2030 | New construction
Dự phòng phát sinh TBA xây mới, cải tạo nâng công suất | 3750 | 2025-2030 | New construction and renovation, capacity expansion
Lắp kháng hạn chế dòng ngắn mạch bao gồm nhưng không giới hạn tại các thanh cái TBA 500 kV Phố Nối, Tây Hà Nội, Hiệp Hòa, Đan Phượng, Bắc Ninh, NĐ Phả Lại, Tràng Bạch |  |  | Short circuit current limit
Cải tạo sơ đồ thanh cái linh hoạt, 4 phân đoạn thanh cái bao gồm nhưng không giới hạn tại các trạm 500 kV Nho Quan, Sơn La, Đông Anh và các trạm Vân Trì, Vật Cách, Long Biên, Trực Ninh, Thái Bình, Hà Đông, Thanh Nghị, Bắc Ninh 2, NĐ Hải Dương |  |  | Limit short circuit current, increase power supply reliability
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | Including but not limited to projects: Replacing, installing electric resistors, capacitor banks, SVC, SVG, FACTS devices, BESS, synchronous compensators...; expanding substation bays, renovating, completing transformer station diagrams in a flexible direction; installing short-circuit current limiting devices, replacing and upgrading devices to ensure synchronous short-circuit current capacity, setting up automatic circuits; replacing devices to ensure synchronous load capacity of lines and transformers; installing, replacing devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...
Sóc Sơn 2 | 750 | 2031-2035 | Renovation and capacity improvement
Văn Điển | 750 | 2031-2035 | Renovation and capacity improvement
Long Biên 2 | 750 | 2031-2035 | Renovation and capacity improvement
Xuân Mai | 750 | 2031-2035 | Renovation and capacity improvement
Chương Mỹ | 500 | 2031-2035 | Renovation and capacity improvement
Ứng Hòa | 750 | 2031-2035 | Renovation and capacity improvement
Hòa Lạc | 750 | 2031-2035 | Renovation and capacity improvement
Cầu Giấy | 500 | 2031-2035 | Renovation and capacity improvement
Hai Bà Trưng | 750 | 2031-2035 | Renovation and capacity improvement
Đan Phượng | 750 | 2031-2035 | Renovation and capacity improvement
Phú Xuyên | 500 | 2031-2035 | Renovation and capacity improvement
Đông Anh 2 | 500 | 2031-2035 | New construction
Đông Anh 3 | 500 | 2031-2035 | New construction
Hòa Lạc 2 | 750 | 2031-2035 | Renovation and capacity improvement
Phúc Thọ | 500 | 2031-2035 | New construction
Thanh Trì | 500 | 2031-2035 | New construction
Thanh Oai | 500 | 2031-2035 | New construction
Vân Trì 500 kV nối cấp | 500 | 2031-2035 | New construction
Vân Trì 2 | 500 | 2031-2035 | New construction
Đình Vũ | 750 | 2031-2035 | Renovation and capacity improvement
Đồ Sơn | 500 | 2031-2035 | Renovation and capacity improvement
An Lão | 750 | 2031-2035 | Renovation and capacity improvement
Thủy Nguyên | 750 | 2031-2035 | Renovation and capacity improvement
Đại Bản | 500 | 2031-2035 | Renovation and capacity improvement
Hải Phòng 2 | 250 | 2031-2035 | New construction
Đình Vũ 2 | 500 | 2031-2035 | New construction
Gia Lộc | 750 | 2031-2035 | Renovation and capacity improvement
Tứ Kỳ | 500 | 2031-2035 | Renovation and capacity improvement
Thanh Hà | 500 | 2031-2035 | Renovation and capacity improvement
Nhị Chiểu | 500 | 2031-2035 | Renovation and capacity improvement
Nam Sách | 500 | 2031-2035 | Renovation and capacity improvement
Thanh Miện | 500 | 2031-2035 | Renovation and capacity improvement
Phố Nối | 750 | 2031-2035 | Renovation and capacity improvement
Phố Cao | 750 | 2031-2035 | Renovation and capacity improvement
Hưng Yên 500 kV nối cấp | 500 | 2031-2035 | Renovation and capacity improvement
Văn Giang | 500 | 2031-2035 | Renovation and capacity improvement
Phố Nối 500 kV nối cấp | 750 | 2031-2035 | Renovation and capacity improvement
Phủ Lý | 750 | 2031-2035 | Renovation and capacity improvement
Thanh Nghị | 750 | 2031-2035 | Renovation and capacity improvement
Lý Nhân | 750 | 2031-2035 | Renovation and capacity improvement
Kim Bảng | 500 | 2031-2035 | New construction
Nam Định 2 | 500 | 2031-2035 | Renovation and capacity improvement
Giao Thủy | 500 | 2031-2035 | Renovation and capacity improvement
Nam Định 2 500 kV nối cấp | 500 | 2031-2035 | New construction
Thái Bình 500 kV nối cấp | 750 | 2031-2035 | Renovation and capacity improvement
Tiền Hải | 500 | 2031-2035 | New construction
Ninh Bình 2 | 750 | 2031-2035 | Renovation and capacity improvement
Tam Điệp | 500 | 2031-2035 | Renovation and capacity improvement
Hà Giang | 500 | 2031-2035 | Renovation and capacity improvement
Hà Giang 2 | 250 | 2031-2035 | New construction
Quảng Uyên | 250 | 2031-2035 | New construction
Lào Cai 500 kV nối cấp | 750 | 2031-2035 | Renovation and capacity improvement
Văn Bàn | 500 | 2031-2035 | Renovation and capacity improvement
Lào Cai 2 | 250 | 2031-2035 | New construction
NLTT Lào Cai 3 (*) | 500 | 2031-2035 | New construction
Đồng Mỏ | 750 | 2031-2035 | Renovation and capacity improvement
TĐ Tuyên Quang | 250 | 2031-2035 | Renovation and capacity improvement
Sơn Dương | 500 | 2031-2035 | New construction
Lục Yên | 500 | 2031-2035 | Renovation and capacity improvement
Đại Từ | 500 | 2031-2035 | Renovation and capacity improvement
Phúc Xuân | 500 | 2031-2035 | New construction
Phú Lương | 500 | 2031-2035 | New construction
Phú Bình 3 | 500 | 2031-2035 | New construction
Phú Thọ 3 | 500 | 2031-2035 | Renovation and capacity improvement
Việt Trì 2 | 500 | 2031-2035 | New construction
Phú Thọ 500 kV nối cấp | 500 | 2031-2035 | New construction
Vĩnh Yên | 750 | 2031-2035 | Renovation and capacity improvement
Bá Thiện | 750 | 2031-2035 | Renovation and capacity improvement
Phúc Yên | 500 | 2031-2035 | Renovation and capacity improvement
Chấn Hưng | 500 | 2031-2035 | Renovation and capacity improvement
Vĩnh Tường 500 kV nối cấp | 500 | 2031-2035 | New construction
Lạng Giang | 500 | 2031-2035 | Renovation and capacity improvement
Yên Dũng | 750 | 2031-2035 | Renovation and capacity improvement
Sơn Động | 500 | 2031-2035 | Renovation and capacity improvement
Tân Yên | 750 | 2031-2035 | Renovation and capacity improvement
Việt Yên | 750 | 2031-2035 | Renovation and capacity improvement
Chũ | 500 | 2031-2035 | New construction
Bắc Ninh | 750 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh 3 | 750 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh 2 | 750 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh 6 | 750 | 2031-2035 | Renovation and capacity improvement
Bắc Ninh 2 500 kV nối cấp | 500 | 2031-2035 | New construction
Bắc Ninh 3 500 kV nối cấp | 500 | 2031-2035 | New construction
Bắc Ninh 10 | 750 | 2031-2035 | New construction
Bắc Ninh 9 | 750 | 2031-2035 | New construction
Quảng Ninh 500 kV nối cấp | 750 | 2031-2035 | Renovation and capacity improvement
Hải Hà 2 | 500 | 2031-2035 | Renovation and capacity improvement
Vân Đồn | 250 | 2031-2035 | New construction
Sìn Hồ | 750 | 2031-2035 | Renovation and capacity improvement
NLTT Lai Châu 3 (*) | 500 | 2031-2035 | New construction
NLTT Lai Châu 4(*) | 500 | 2031-2035 | New construction
Sông Mã | 500 | 2031-2035 | Renovation and capacity improvement
Yên Thủy | 500 | 2031-2035 | Renovation and capacity improvement
Lương Sơn | 250 | 2031-2035 | New construction
Hòa Bình 1 (*) | 250 | 2031-2035 | New construction
Thiệu Hóa | 500 | 2031-2035 | Renovation and capacity improvement
Thiệu Yên | 500 | 2031-2035 | Renovation and capacity improvement
Tĩnh Gia 500 kV nối cấp | 500 | 2031-2035 | New construction
Quỳ Hợp | 500 | 2031-2035 | Renovation and capacity improvement
Tương Dương | 500 | 2031-2035 | Renovation and capacity improvement
Hoàng Mai 2 | 500 | 2031-2035 | Renovation and capacity improvement
Hưng Nguyên | 500 | 2031-2035 | New construction
Cửa Lò | 500 | 2031-2035 | New construction
Can Lộc | 500 | 2031-2035 | Renovation and capacity improvement
Lộc Hà | 250 | 2031-2035 | New construction
Dự phòng phát sinh TBA xây mới, cải tạo nâng công suất | 2750 | 2031-2035 | New construction and renovation, capacity expansion
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | Including but not limited to projects: Replacing, installing electric resistors, capacitor banks, SVCs, SVGs, FACTS devices, BESSs, synchronous compensators...; expanding substation bays, renovating and completing substation diagrams in a flexible direction; installing short-circuit current limiting devices, replacing and upgrading devices to ensure synchronous short-circuit current capacity, setting up automatic circuits; replacing devices to ensure synchronous load capacity of transmission lines and transformers; installing and replacing devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...

## Table 6 220 kV lines in the Nor
Name | No. of circuits × km | Time | Note
Đông Anh 500 kV - Vân Trì | 2x16 | 2025-2030 | New construction
Đại Mỗ (Mỹ Đình) - Rẽ Tây Hà Nội - Thanh Xuân | 4x2 | 2025-2030 | Connection to Dai Mo 220 kV Substation
Tây Hà Nội - Thanh Xuân | 4x16 | 2025-2030 | Connection to Thanh Xuan 220 kV Substation
Cải tạo đường dây 220 kV Sơn Tây - Vĩnh Yên 01 mạch thành 2 mạch | 2x30 | 2025-2030 | Convert one circuit into two circuits, and simultaneously change the connection into a two-circuit line Son Tay - Vinh Yen
Chương Mỹ - Rẽ Hòa Bình - Hà Đông | 2x2 | 2025-2030 | Connection to 220 kV Chuong My Substation
Đan Phượng 500 kV - Mê Linh | 2x15 | 2025-2030 | New construction
Đan Phượng 500 kV - Cầu Giấy | 2x20 | 2025-2030 | Overhead lines and underground cables (inner city), connecting to 220 kV Cau Giay substation
Đấu nối Đan Phượng 500 kV - rẽ Chèm - Vân Trì và Chèm - Tây Hồ | 4x11 | 2025-2030 | New construction
Nam Hà Nội 500 kV - rẽ Hà Đông - Phủ Lý | 4x5 | 2025-2030 | New construction
Hai Bà Trưng - Mai Động | 2x3 | 2025-2030 | Underground cable, connecting 220 kV Hai Ba Trung substation
Hai Bà Trưng - Thành Công | 2x5 | 2025-2030 | Underground cable, connecting 220 kV Hai Ba Trung substation
Long Biên - Mai Động | 2x15 | 2025-2030 | New construction
Long Biên 2 - Rẽ Mai Động - Long Biên | 4x3 | 2025-2030 | Connection to 220 kV Long Bien 2 Substation
Hưng Yên 1 500 kV - Long Biên 2 | 2x20 | 2025-2030 | Connection to 220 kV side of 500 kV Hung Yen 1 substation
Hưng Yên 1 500 kV - Rẽ Phố Nối - Thường Tín | 4x4 | 2025-2030 | New construction
Mạch 2 Hà Đông - Ứng Hòa - Phủ Lý | 2x40 | 2025-2030 | Converting one circuit into two circuits, expanding two bays at Ung Hoa 220 kV station
Mê Linh - Rẽ Sóc Sơn - Vân Trì (mạch 1) | 2x2 | 2025-2030 | Connection to 220 kV Me Linh Substation
Mê Linh - Rẽ Sóc Sơn - Vân Trì (mạch 2) | 2x2 | 2025-2030 | Connecting 220 kV Me Linh substation. Changing the connection of 220 kV Vinh Yen 500 kV - Me Linh and Me Linh - Van Tri to Vinh Yen - Van Tri when the short-circuit current in the area increases higher than the allowable limit.
Nam Hà Nội 500 kV - Phú Xuyên | 2x15 | 2025-2030 | Connection to 220 kV Phu Xuyen Substation
Hòa Bình - Tây Hà Nội mạch 4 | 1x50 | 2025-2030 | New construction, renovating the old Hoa Binh - Ha Dong line 3. Synchronize with renovating the 220kV distribution yard diagram of Hoa Binh power plant to limit short circuit current.
Nâng khả năng tải 500 kV Thường Tín - Phố Nối | 2x34 | 2025-2030 | Increase the load capacity of 1 circuit Thuong Tin - 220 kV Pho Noi substation, 1 circuit Thuong Tin - 500 kV Pho Noi substation
Nâng khả năng tải Hiệp Hòa - Sóc Sơn | 2x10 | 2025-2030 | Increase the load capacity of two circuits of the 220kV Hiep Hoa - Soc Son line, remove the remaining two circuits to limit short-circuit current.
Nâng khả năng tải Vân Trì - Tây Hồ - Chèm | 2x20 | 2025-2030 | Ensuring electricity supply in Hanoi
Nâng khả năng tải Xuân Mai - Hà Đông | 1x25 | 2025-2030 | Renovation
Sóc Sơn 2 - Rẽ Hiệp Hòa - Đông Anh | 2x3 | 2025-2030 | Connection to 220 kV Soc Son 2 substation
Sơn Tây 500 kV - Hòa Lạc | 2x12 | 2025-2030 | New construction
Sơn Tây 500 kV - Hòa Lạc 2 | 2x15 | 2025-2030 | New construction
Sơn Tây 500 kV - Rẽ Sơn Tây - Vĩnh Yên | 4x5 | 2025-2030 | New construction
Tây Hà Nội 500 kV - Hòa Lạc | 2x14 | 2025-2030 | New construction
Ứng Hòa - Rẽ Hà Đông - Phủ Lý | 2x1 | 2025-2030 | Connection to 220 kV Ung Hoa Substation
Văn Điển - Rẽ Hà Đông - Thường Tín | 4x7 | 2025-2030 | Connection to 220 kV Van Dien substation
NLTT Hà Nội 2 - Sơn Tây (*) | 2x15 | 2025-2030 | New construction
Dương Kinh - Rẽ Đồng Hòa - Đình Vũ | 4x3 | 2025-2030 | Connecting 220 kV Duong Kinh substation, and simultaneously changing the connection from Hai Duong 2 - Dong Hoa and Dong Hoa - Dinh Vu to Hai Duong 2 - Dinh Vu
An Lão - Rẽ Đồng Hòa - Thái Bình | 4x2 | 2025-2030 | Connection to 220 kV An Lao Substation
Cát Hải - Đình Vũ | 2x12 | 2025-2030 | In case the 220 kV Dinh Vu transformer station cannot be expanded, consider connecting a 220 kV Dinh Vu - Duong Kinh line circuit.
Đại Bản - Rẽ Hải Dương 2 - Dương Kinh | 4x2 | 2025-2030 | Connection to Dai Ban 220 kV Substation
Đồ Sơn - Dương Kinh | 2x8 | 2025-2030 | Connection to 220 kV Do Son Substation
Hải Phòng 2 500 kV - Rẽ Đồng Hòa - Vật Cách | 4x10 | 2025-2030 | New construction
Hải Phòng 2 500 kV - Đại Bản | 4x5 | 2025-2030 | New construction, consideration of connecting to Dai Ban 220kV substation
Hải Phòng 500 kV - Dương Kinh | 2x8 | 2025-2030 | New construction
Hải Phòng 500 kV - Tiên Lãng | 2x14 | 2025-2030 | Connection to 220 kV Tien Lang Substation
Nam Hòa - Cát Hải | 2x12 | 2025-2030 | New construction
BB 1 - Đồ Sơn (*) | 2x10 | 2025-2030 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Gia Lộc - Rẽ NĐ Hải Dương - Phố Nối | 4x5 | 2025-2030 | New construction
500 kV Hải Phòng - Gia Lộc | 2x32 | 2025-2030 | New construction
Gia Lộc 500 kV - Rẽ Gia Lộc - Hải Phòng 500 kV | 4x5 | 2025-2030 | Connecting 500 kV Gia Loc substation, in case land fund cannot be arranged to connect Gia Loc 220 kV
Nhị Chiểu - Rẽ Mạo Khê - Hải Dương 2 | 4x2 | 2025-2030 | Connection to 220 kV Nhi Chieu Substation
Tân Việt - Rẽ Gia Lộc - Phố Nối | 4x3 | 2025-2030 | Connection to Tan Viet 220 kV Substation
Thanh Hà - Rẽ 500 kV Hải Phòng - Gia Lộc | 2x12 | 2025-2030 | Connection to Thanh Ha 220 kV Substation
Tứ Kỳ - Rẽ Hải Phòng 500 kV- Gia Lộc | 4x4 | 2025-2030 | New construction
Gia Lộc 500 kV - Thanh Miện | 2x11 | 2025-2030 | New construction
Nam Sách - NĐ Hải Dương | 2x11 | 2025-2030 | New construction
Bãi Sậy - Kim Động | 2x11 | 2025-2030 | Connection to Bai Say 220 kV Substation
Hưng Yên 2 500 kV - Đồng Văn | 2x14 | 2025-2030 | Connection of 500 kV Hung Yen 2 Substation
Hưng Yên 2 500 kV - Rẽ Kim Động - Phố Cao | 4x5 | 2025-2030 | Connection of 500 kV Hung Yen 2 Substation
Văn Giang - Rẽ Hưng Yên 1 500 kV - Thường Tín 500 kV | 4x2 | 2025-2030 | Connection to 220 kV Van Giang Substation
Mạch 2 Nho Quan - Phủ Lý | 1x40 | 2025-2030 | New construction and renovation of 1 circuit into 2 circuits
Đồng Văn - Phủ Lý | 2x17 | 2025-2030 | Connecting 220 kV Dong Van substation, in case Phu Ly cannot expand the road, connecting Ha Dong - Phu Ly
Lý Nhân - Rẽ Thanh Nghị - Thái Bình | 4x2 | 2025-2030 | Connection to 220 kV Ly Nhan Substation
Hải Hậu - Trực Ninh | 2x17 | 2025-2030 | Connection to 220 kV Hai Hau Substation
Nam Định 2 - Rẽ Trực Ninh - Ninh Bình và Trực Ninh - Nam Định | 4x2 | 2025-2030 | Connection to 220 kV Nam Dinh 2 Substation
NĐ Nam Định 500 kV - Hải Hậu | 2x10 | 2025-2030 | Connection to 500 kV Nam Dinh Substation
NĐ Nam Định 500 kV - Hậu Lộc | 2x47 | 2025-2030 | Connection to 500 kV Nam Dinh Substation
NĐ Nam Định 500 kV - Nam Định 3 | 2x18 | 2025-2030 | Synchronize with the progress of specialized load development
NĐ Nam Định 500 kV - Ninh Bình 2 | 2x30 | 2025-2030 | Large cross-section phase wire. Connection to 500 kV Nam Dinh substation
Nghĩa Hưng - Rẽ NĐ Nam Định 500 kV - Hậu Lộc | 4x2 | 2025-2030 | Connection to 220 kV Nghia Hung Substation
Giao Thủy - rẽ LNG Thái Bình - Trực Ninh | 4x4 | 2025-2030 | New construction, connection of 220kV Giao Thuy substation
Vũ Thư - Rẽ Thái Bình - Nam Định và Thái Bình - Ninh Bình | 4x2 | 2025-2030 | Connection to 220 kV Vu Thu Substation
LNG Thái Bình - Tiên Lãng | 2x56 | 2025-2030 | New construction, synchronized power source
LNG Thái Bình - Trực Ninh | 2x50 | 2025-2030 | New construction, synchronized power source
Quỳnh Phụ - Rẽ Thái Bình - Đồng Hòa | 4x2 | 2025-2030 | Connection to 220 kV Quynh Phu Substation
Thái Bình 500 kV - Rẽ Thái Bình - Kim Động | 4x5 | 2025-2030 | Connection to 220 kV Thai Binh 500 kV side
Thái Bình 500 kV - Thanh Nghị | 2x53 | 2025-2030 | New construction
Cải tạo đường dây 220 kV Gia Viễn - Tam Điệp - Bỉm Sơn 01 mạch thành 02 mạch | 2x34 | 2025-2030 | Gia Vien - Tam Diep - Bim Son 220kV Line replaces Ninh Binh - Tam Diep - Bim Son 220kV Line in case of relocation of Ninh Binh 220kV Substation
Gia Viễn - Nam Định | 2x13 | 2025-2030 | Gia Vien - Nam Dinh connection transfer, implemented in case of moving Ninh Binh 220 kV substation
Gia Viễn - Rẽ Nho Quan 500 kV - Ninh Bình | 4x1 | 2025-2030 | Connection to Gia Vien 220 kV Substation
Nâng khả năng tải Nho Quan 500 kV- Ninh Bình | 2x26 | 2025-2030 | Renovation
Ninh Bình 2 - Rẽ Ninh Bình - Thái Bình | 2x12 | 2025-2030 | Connection to 220 kV Ninh Binh 2 substation
Tam Điệp - Rẽ Bỉm Sơn - Ninh Bình | 4x5 | 2025-2030 | Connect the 220 kV Tam Diep substation on one circuit first, connect the remaining circuit synchronously with the 220 kV Gia Vien - Tam Diep - Bim Son line
Nhà máy điện linh hoạt Ninh Bình - Rẽ Nam Định 500 kV - Hậu Lộc | 2x16 | 2025-2030 | New and synchronous construction of Ninh Binh Flexible Power Plant
Bắc Quang - Biên giới Việt Nam - Trung Quốc (địa phận tỉnh Hà Giang) | 2x55 | 2025-2030 | Increase purchase of Chinese electricity
Nâng khả năng tải Hà Giang - Rẽ TĐ Bắc Mê và Hà Giang - Thái Nguyên | 42 + 51 | 2025-2030 | Increase the load capacity of AC410 sections on the Ha Giang - Bac Me Terminal (42km) and Ha Giang - Thai Nguyen (51km) routes.
Treo dây mạch 2 Hà Giang - Biên giới Việt Nam - Trung Quốc | 1x30 | 2025-2030 | Increase purchase of Chinese electricity
Bảo Lâm - Bắc Mê | 2x30 | 2025-2030 | Releasing the capacity of small hydropower plants in Ha Giang
Cao Bằng - Lạng Sơn | 2x120 | 2025-2030 | New construction
Bát Xát - 500 kV Lào Cai | 2x47 | 2025-2030 | Connection to 220 kV Bat Xat Substation
Đấu nối 500 kV Lào Cai | 4x5 | 2025-2030 | Connecting to 500 kV Lao Cai substation, Bao Thang - Yen Bai branch
Bắc Hà - Lào Cai 500 kV | 1x50 | 2025-2030 | Synchronize with regional power source scale and progress
TĐ Bắc Hà - chuyển đấu nối 500 kV Lào Cai | 1x5 | 2025-2030 | Reduce the load on the 220kV Bao Thang - Lao Cai 500kV line
Than Uyên - 500 kV Lào Cai | 2x73 | 2025-2030 | Connecting 220 kV Than Uyen substation, clearing small hydropower plants
Văn Bàn - Rẽ Than Uyên - Lào Cai 500 kV | 4x10 | 2025-2030 | Connecting to 220 kV Van Ban substation, releasing small hydropower capacity
Nâng khả năng tải Lào Cai 500 kV- Lục Yên | 2x90 | 2025-2030 | Renovation
Bắc Kạn 1 - Bắc Kạn (*) | 2x10 | 2025-2030 | New construction
Đồng Mỏ - Rẽ Bắc Giang - Lạng Sơn | 4x1 | 2025-2030 | Connection to 220 kV Dong Mo Substation
Lạng Sơn 1 - Đồng Mỏ (*) | 2x60 | 2025-2030 | Synchronize with regional power source scale and progress
Lạng Sơn 2 - Lạng Sơn 1 500 kV (*) | 2x20 | 2025-2030 | New construction
TĐ Yên Sơn - Rẽ TĐ Tuyên Quang - Tuyên Quang | 2x8 | 2025-2030 | Synchronous Yen Son
Nghĩa Lộ - Việt Trì (500 kV Việt Trì) | 2x93 | 2025-2030 | Small hydropower clearance
Huội Quảng - Nghĩa Lộ | 2x103 | 2025-2030 | Small hydropower clearance
Chuyển đấu nối Bắc Quang - Lục Yên | 2x1 | 2025-2030 | Transferring connection from Bac Quang to Luc Yen
Lục Yên - rẽ 220 kV Lào Cai - Yên Bái | 4x5 | 2025-2030 | New construction
Nâng khả năng tải Lục Yên - Yên Bái | 2x58 | 2025-2030 | Increase load capacity, increase purchase of Chinese electricity
Nâng khả năng tải Yên Bái - Tuyên Quang | 2x36 | 2025-2030 | Increase load capacity, increase purchase of Chinese electricity
Yên Bái 2 - Yên Bái 500 kV (*) | 2x10 | 2025-2030 | New construction
Yên Bái 500 kV-Rẽ Yên Bái - Tuyên Quang (*) | 4x5 | 2025-2030 | New construction
Yên Bái 1 - Yên Bái 500 kV (*) | 2x10 | 2025-2030 | New construction
Đấu nối TĐ An Bình (*) | 2x10 | 2025-2030 | New construction, synchronization of power sources. Document No. 27/UBND-CN dated January 4, 2025 proposes a transitional connection on the 220kV Bao Thang - Yen Bai line. The specific connection plan is accurate during the project implementation phase.
Đấu nối TĐ An Thịnh (*) | 2x10 | 2025-2030 | New construction, synchronization of power sources. Document No. 27/UBND-CN dated January 4, 2025 proposes a transitional connection on the 220kV Bao Thang - Yen Bai line. The specific connection plan is accurate during the project implementation phase.
Đấu nối TĐ Việt Thành (*) | 2x10 | 2025-2030 | New construction, synchronization of power sources. Document No. 27/UBND-CN dated January 4, 2025 proposes a transitional connection on the 220kV Bao Thang - Yen Bai line. The specific connection plan is accurate during the project implementation phase.
NLTT Thái Nguyên 2 - Rẽ Tuyên Quang - Thái Nguyên 500 kV (*) | 2x10 | 2025-2030 | New construction, synchronized power source
Phú Bình 2 - Rẽ Thái Nguyên - Bắc Giang | 2x13 | 2025-2030 | Connection to 220 kV Phu Binh 2 Substation
500 kV Hiệp Hòa - Phú Bình 2 | 2x14 | 2025-2030 | Connection to 220 kV Phu Binh 2 Substation
500 kV Thái Nguyên - Rẽ Lưu Xá - Phú Bình | 2x13 | 2025-2030 | Connection to 220 kV side of 500 kV Thai Nguyen substation
500 kV Thái Nguyên - Rẽ Malungtang - Thái Nguyên | 2x14 | 2025-2030 | Connection to 220 kV side of 500 kV Thai Nguyen substation
500 kV Thái Nguyên - Rẽ Tuyên Quang (TBA) - Phú Bình | 2x14 | 2025-2030 | Connection to 220 kV side of 500 kV Thai Nguyen substation
Đại Từ - Rẽ Tuyên Quang - Thái Nguyên 500 kV | 4x2 | 2025-2030 | Connection to Dai Tu 220 kV Substation
Đấu nối Yên Thế 500 kV | 4x4 | 2025-2030 | New construction
Hiệp Hòa 2 - Rẽ Hiệp Hòa 500 kV - Phú Bình 2 | 4x5 | 2025-2030 | Connection to 220 kV Hiep Hoa 2 Substation
Nâng khả năng tải Hiệp Hòa - Phú Bình | 1x11 | 2025-2030 | Increase the load capacity of ACSR410 circuit
Nâng khả năng tải Thái Nguyên - Lưu Xá - Phú Bình | 1x30 | 2025-2030 | Renovation
Sông Công - Rẽ Tuyên Quang - Phú Bình | 2x1 | 2025-2030 | Connection to 220 kV Song Cong Substation
Tân Yên - Rẽ Yên Thế - Việt Yên | 4x5 | 2025-2030 | Connection to Tan Yen 220 kV Substation
Yên Thế 500 kV - Việt Yên | 2x25 | 2025-2030 | Connection to 220 kV Viet Yen Substation
500 kV Việt Trì - Bá Thiện (500 kV Vĩnh Yên) | 2x50 | 2025-2030 | New construction
Phú Thọ 2 - Rẽ Sơn La - Việt Trì | 2x1 | 2025-2030 | Connection to 220 kV Phu Tho 2 Substation
Nâng khả năng tải 500 kV Việt Trì - Việt Trì | 2x10 | 2025-2030 | Renovation
Nâng khả năng tải 500 kV Việt Trì - Vĩnh Tường | 1x27 | 2025-2030 | Renovation
Nâng khả năng tải 500 kV Việt Trì - Vĩnh Yên | 1x36 | 2025-2030 | Renovation
Phú Thọ 3 - Rẽ Nghĩa Lộ - 500 kV Việt Trì | 4x22 | 2025-2030 | Connection to 220 kV Phu Tho 3 Substation
Bá Thiện (Vĩnh Yên 500 kV) - Rẽ Vĩnh Yên - Sóc Sơn | 2x13 | 2025-2030 | Connecting to Ba Thien 220kV substation. Combining renovation and increasing the load capacity of the existing line from Vinh Yen 220kV to the intersection point.
Chấn Hưng - Rẽ 500 kV Việt Trì - 220 kV Vĩnh Yên | 2x2 | 2025-2030 | Connection to 220 kV Chan Hung Substation
Phúc Yên-Rẽ Vĩnh Yên 500 kV - 220 kV Vĩnh Yên | 2x1 | 2025-2030 | New construction
Tam Dương - Rẽ 500 kV Việt Trì - Bá Thiện (500 kV Vĩnh Yên) | 4x4 | 2025-2030 | Connection to Tam Duong 220 kV Substation
Vĩnh Tường - Vĩnh Yên | 2x17 | 2025-2030 | New construction and renovation, conversion of connection to 02-circuit line Vinh Tuong - Vinh Yen
Vĩnh Yên 500 kV - Mê Linh | 2x28 | 2025-2030 | Replacing the 220 kV Me Linh - Ba Thien line in the adjusted Power Plan VII. The 220 kV Ba Thien station is connected to the 500 kV Vinh Yen station.
NĐ Phả Lại - Bắc Giang Mạch 2 | 2x27 | 2025-2030 | Convert 1 circuit into 2 circuits
Bắc Giang 1 - Lạng Sơn 1 (*) | 2x35 | 2025-2030 | Synchronize with regional power source scale and progress
Bắc Giang 500 kV - Rẽ NMNĐ An Khánh Bắc Giang - Lạng Sơn | 4x8 | 2025-2030 | 220 kV connection to 500 kV Bac Giang substation
Đấu nối NMNĐ An Khánh Bắc Giang | 4x14 | 2025-2030 | Synchronizing An Khanh Bac Giang Thermal Power Plant, connecting on 220 kV Bac Giang - Lang Son line
Đồng Mỏ - Sơn Động | 2x60 | 2025-2030 | New construction
Lạng Giang - Rẽ Bắc Giang - Thái Nguyên | 2x1 | 2025-2030 | Connection of 220 kV Lang Giang transformer station
Yên Dũng - Rẽ NĐ Phả Lại - Quang Châu | 2x1 | 2025-2030 | Connection to Yen Dung 220 kV Substation
Bắc Ninh 4 - Đông Anh | 2x14 | 2025-2030 | Connection to 220 kV Bac Ninh 4 Substation
Bắc Ninh 5 - Rẽ Bắc Ninh 500 kV - Phố Nối | 2x7 | 2025-2030 | Connection to 220 kV Bac Ninh 5 substation
Bắc Ninh 500 kV - Bắc Ninh | 2x10 | 2025-2030 | Synchronize with the connection of 220kV Pha Lai - Bac Ninh and Bac Ninh - Quang Chau lines to Pha Lai - Quang Chau to limit short-circuit current.
Bắc Ninh 500 kV - Bắc Ninh 4 | 2x14 | 2025-2030 | New construction
Bắc Ninh 500 kV - Rẽ Bắc Ninh 2 - Phố Nối | 4x3 | 2025-2030 | Connection to 220 kV Bac Ninh 500 kV
Bắc Ninh 6 - Rẽ Phả Lại - 500 kV Phố Nối | 2x3 | 2025-2030 | Connecting 220 kV Bac Ninh 6 substation, consider using 04-circuit poles before 02 circuits
Bắc Ninh 7 - Rẽ Đông Anh 500 kV - Bắc Ninh 4 | 4x2 | 2025-2030 | New construction
Cộng Hòa - Rẽ Cẩm Phả - Hải Hà | 4x2 | 2025-2030 | New construction
Biên giới Việt Nam - Trung Quốc - Móng Cái | 2x15 | 2025-2030 | New construction to serve increased purchase of Chinese electricity
Hải Hà - Móng Cái | 2x40 | 2025-2030 | New construction
Hải Hà - Hải Hà 2 | 2x10 | 2025-2030 | New construction, replacement of Hai Ha - Hai Ha Industrial Park power line in the VIII Master Plan
Khe Thần - Rẽ Tràng Bạch - Hoành Bồ | 2x2 | 2025-2030 | Connection to Khe Than 220 kV Substation
Nâng khả năng tải Quảng Ninh - Hoành Bồ | 2x20 | 2025-2030 | Renovation
Quảng Ninh 1 - Rẽ Hoành Bồ - NĐ Sơn Động và Hoành Bồ - Tràng Bạch (*) | 4x5 | 2025-2030 | Synchronize with regional power source scale and progress
Yên Hưng - Nam Hòa | 2x29 | 2025-2030 | Connection to 220 kV Nam Hoa Substation
NLTT Quảng Ninh 2 - Cộng Hòa (*) | 2x16 | 2025-2030 | New construction
Quảng Ninh 2 500 kV - Rẽ Yên Hưng - Nam Hòa | 4x15 | 2025-2030 | New construction
Quảng Ninh 2 500 kV - Rẽ - Hoành Bồ - Tràng Bạch | 2x5 | 2025-2030 | New construction
Pắc Ma - Mường Tè | 2x31 | 2025-2030 | Release TD
Lai Châu 500 kV - Phong Thổ | 2x60 | 2025-2030 | Releasing the capacity of the power plant, reducing the load of Lai Chau 500 kV substation, large cross-section phase wire
Mường Tè - Sìn Hồ | 2x35 | 2025-2030 | Power generation capacity in Muong Te area
Nậm Ou 7 - Lai Châu | 2x65 | 2025-2030 | Connecting Nam Ou 5, 6, 7 power plants (Laos). The entire route is 2x97km, 2x65km in Vietnam. Synchronizing power source from Laos.
Phong Thổ - Than Uyên | 2x88 | 2025-2030 | Small hydropower clearance
Sìn Hồ-Rẽ Lai Châu 500 kV - Phong Thổ | 4x5 | 2025-2030 | Connecting 220 kV Sin Ho substation, relieving power source in the area
NLTT Lai Châu 1 - Than Uyên (*) | 2x10 | 2025-2030 | New construction
NLTT Lai Châu 2 - Than Uyên (*) | 2x10 | 2025-2030 | New construction
Than Uyên 500 kV - Than Uyên | 2x10 | 2025-2030 | New construction, Phong Tho - Than Uyen connection transfer
Than Uyên 500 kV - Rẽ TĐ Bản Chát - Than Uyên | 4x5 | 2025-2030 | New construction
500 kV Sơn La - Điện Biên | 2x133 | 2025-2030 | Connection to 220 kV Dien Bien Substation
Điện Biên 1 - Điện Biên (*) | 2x23 | 2025-2030 | Synchronize with regional power source scale and progress
Điện Biên 1 - Lai Châu (*) | 2x52 | 2025-2030 | Synchronize with regional power source scale and progress
Nậm Ou 5 - Điện Biên | 2x22 | 2025-2030 | Connecting Nam Ou 5, 6, 7 Hydropower Plants (Laos). The entire route is 2x73km, 2x22km in Vietnam. Synchronized with hydropower sources from Laos.
Điện Biên 2 - Điện Biên 500 kV (*) | 2x18 | 2025-2030 | New construction
Điện Biên 500 kV - Rẽ Điện Biên 1 - Điện Biên (*) | 4x5 | 2025-2030 | New construction
Mộc Châu - Rẽ đấu nối TĐ Trung Sơn | 2x35 | 2025-2030 | Connection to 220 kV Moc Chau Substation
Nâng khả năng tải 500 kV Sơn La - Mường La | 1x21 | 2025-2030 | Synchronize with regional power source scale and progress
Nâng khả năng tải 500 kV Sơn La - Sơn La | 1x41 | 2025-2030 | Synchronize with regional power source scale and progress
Nâng khả năng tải Huội Quảng - Sơn La | 2x20 | 2025-2030 | New construction
Phù Yên - Rẽ Sơn La - Việt Trì | 2x7 | 2025-2030 | Connection to 220 kV Phu Yen substation (specialized load power supply)
Sơn La 1 - Rẽ Sơn La - Suối Sập 2A (*) | 2x5 | 2025-2030 | Synchronize with regional power source scale and progress
Sông Mã - Sơn La 500 kV(*) | 2x83 | 2025-2030 | Unlocking small hydropower capacity
Sơn La 2 - Sơn La (*) | 2x35 | 2025-2030 | New construction
Sơn La 3 - Sơn La 1 500 kV (*) | 2x20 | 2025-2030 | New construction
Sơn La 4 - Sơn La 1 500 kV (*) | 2x20 | 2025-2030 | New construction
Sơn La 5 - Sơn La 1 500 kV (*) | 2x20 | 2025-2030 | New construction
Sơn La 6 - Rẽ Huội Quảng - Nghĩa Lộ (*) | 2x20 | 2025-2030 | New construction
Đấu nối Tân Lạc | 6x5 | 2025-2030 | Tan Lac - Hoa Binh - Yen Thuy branch and Trung Son power plant connection transfer, forming 220 kV double-circuit lines Hoa Binh - Tan Lac, Tan Lac - Yen Thuy and Tan Lac - Trung Son power plant - Hoi Xuan power plant
Thanh Hóa 500 kV - Sầm Sơn | 2x36 | 2025-2030 | Connection to 220 kV Sam Son Substation
500 kV Thanh Hóa - Hậu Lộc | 2x35 | 2025-2030 | Connection to Hau Loc 220 kV Substation
Đồng Vàng - Rẽ NĐ Nghi Sơn - Nông Cống | 4x4 | 2025-2030 | Synchronize with load development progress
Mạch 3 Thanh Hóa - Nghi Sơn - Quỳnh Lưu | 1x83 | 2025-2030 | Hanging wire circuit 2
Nâng khả năng tải Nông Cống - 500 kV Thanh Hóa | 2x26 | 2025-2030 | Renovation in case of Nghi Son 2 Power Plant clearance via 220 kV grid.
NĐ Nghi Sơn - Rẽ Nông Cống - Quỳnh Lưu | 2x10 | 2025-2030 | Change the connection of Nong Cong - Nghi Son and Nghi Son - Quynh Luu to Nong Cong - Quynh Luu. Replace the 220 kV line Nghi Son ND - Nghi Son - Vinh branch
Nghi Sơn 2 - Rẽ NĐ Nghi Sơn - Nông Cống | 4x2 | 2025-2030 | Connecting Nghi Son 2 220kV station, synchronized with the progress of specialized load development
Nông Cống - Nghi Sơn - chuyển đấu nối NĐ Nghi Sơn | 2x42 | 2025-2030 | Phase 2 of Nghi Son ND line - Nong Cong - Quynh Luu branch, restoring the current status of Nong Cong - Quynh Luu 220 kV transmission line
TĐ Nam Sum (Lào) - Nông Cống | 2x129 | 2025-2030 | Another name of the 220 kV line "220 kV Nam Sum - Nong Cong shunting station (line section in Vietnam territory)", was approved in document No. 1889/TTg-CN dated December 27, 2018 of the Prime Minister. Synchronized with Nam Sum Lao Power Plant
Thanh Hóa 1 - Rẽ Nghi Sơn - Nông Cống (*) | 4x2 | 2025-2030 | Synchronize with regional power source scale and progress
Thanh Hóa 500 kV - Bỉm Sơn | 2x36 | 2025-2030 | Converting 1 circuit into 2 circuits of 220 kV Ba Che - Bim Son line
Thiệu Hóa - Thanh Hóa 500 kV | 2x5 | 2025-2030 | Connection to 220 kV Thieu Hoa Substation
Đường dây đấu nối TBA 220 kV Lọc hoá dầu Nghi Sơn | 2x10 | 2025-2030 | New construction
Thiệu Hóa - Thiệu Yên | 2x25 | 2025-2030 | Connection to 220 kV Thieu Yen Substation
TĐ Hồi Xuân - Rẽ Trung Sơn - Nho Quan | 2x16 | 2025-2030 | New construction
TĐ Hồi Xuân - Bá Thước | 2x30 | 2025-2030 | Connection to 220 kV Ba Thuoc Substation
Tĩnh Gia - Rẽ Nông Cống - Nghi Sơn | 2x8 | 2025-2030 | Connection to 220 kV Tinh Gia Substation
NLTT Nghề An 1 - Nam cấm (*) | 2x20 | 2025-2030 | New construction
NLTT Nghệ An 2 - Quỳ Hợp (*) | 2x20 | 2025-2030 | New construction
ĐG Trường Sơn - Đô Lương (*) | 2x40 | 2025-2030 | New construction
Đô Lương - Nam Cấm | 2x36 | 2025-2030 | Releasing capacity of Lao Hydropower Plant and Western Nghe An Hydropower Plant
Tương Dương - Đô Lương | 2x81 | 2025-2030 | Synchronization of Nam Mo TD cluster (Laos)
Quỳnh Lưu 500 kV rẽ Nghi Sơn - Quỳnh Lưu | 4x10 | 2025-2030 | Connection to 220 kV Quynh Luu 500 kV side
Hoàng Mai - Quỳnh Lưu 500 kV | 2x10 | 2025-2030 | New construction
Hoàng Mai - rẽ Nghi Sơn - Hưng Đông | 2x10 | 2025-2030 | New construction
Hoàng Mai 2 - Rẽ Quỳnh Lưu 500kV - Hoàng Mai | 2x5 | 2025-2030 | New construction
Mỹ Lý - Bản Vẽ | 2x72 | 2025-2030 | Synchronous My Ly Stadium
Nâng khả năng tải Hưng Đông - Quỳnh Lưu và Hưng Đông - Nghi Sơn | 2x100 | 2025-2030 | Renovate and increase the load capacity of 2 circuits of the 220 kV Hung Dong - Nghi Son and Hung Dong - Quynh Luu lines or consider the plan to renovate the Hung Dong - Nghi Son line from 1 circuit to 2 circuits if the bays at Nghi Son and Hung Dong substations can be expanded. Releasing capacity of Lao Hydropower Plant and Western Nghe An Hydropower Plant
Quỳ Hợp - Quỳnh Lưu 500 kV | 2x5 | 2025-2030 | Connecting to Quy Hop 220 kV substation, releasing TDN capacity.
TĐ Nậm Mô 1 - Rẽ Mỹ Lý - Bản Vẽ | 2x18 | 2025-2030 | Synchronous Nam Mo 1 TD (Vietnam)
Tương Dương - Quỳ Hợp | 2x80 | 2025-2030 | Liberate the Lao People's Democratic Republic and increase electricity imports to Laos
Vũng Áng 2 - Rẽ Vũng Áng - 500 kV NĐ Vũng Áng | 2x2 | 2025-2030 | Connecting 220 kV Vung Ang 2 substation, synchronized with the progress of specialized load development
Vũng Áng - 500 kV NĐ Vũng Áng | 2x13 | 2025-2030 | Connection to 220 kV Vung Ang Substation
Can Lộc - Rẽ Hà Tĩnh - Hưng Đông | 4x2 | 2025-2030 | Connection to 220 kV Can Loc Substation
Hà Tĩnh 1 - Rẽ Vũng Áng - Hà Tĩnh (*) | 4x4 | 2025-2030 | Synchronize with regional power source scale and progress
Nâng khả năng tải Hà Tĩnh - Hưng Đông | 2x66 | 2025-2030 | Prevent overload in dry season. Improve the load capacity of 2 existing power lines.
NLTT Hà Tĩnh 2 - Hà Tĩnh 2 500kV (*) | 2x20 | 2025-2030 | New construction
NLTT Hà Tĩnh 3-Hà Tĩnh 2 500kV (*) | 2x20 | 2025-2030 | New construction
NLTT Hà Tĩnh 4 - Hà Tĩnh 2 500kV (*) | 2x20 | 2025-2030 | New construction
NLTT Hà Tĩnh 5-Hà Tĩnh 2 500kV (*) | 2x20 | 2025-2030 | New construction
TĐ Bản Chát MR - Rẽ Bản Chát - Than Uyên | 2x1 | 2025-2030 | New construction, synchronized power source. Proposed plan in EVN Document No. 862/EVN-KH dated February 11, 2025. Specific connection plan is accurate during project implementation phase.
TĐ Tuyên Quang MR - TĐ Tuyên Quang | 1x1 | 2025-2030 | New construction, synchronized power source. Proposed plan in EVN Document No. 862/EVN-KH dated February 11, 2025. Specific connection plan is accurate during project implementation phase.
TĐ Sông Lô 9 - rẽ Tuyên Quang - Phú Bình | 2x2 | 2025-2030 | Synchronize Song Lo 9 Hydropower Plant
TĐ Tuyên Quang - Rẽ Hà Giang - Thái Nguyên và TĐ Bắc Mê - Thái Nguyên | 4x1 | 2025-2030 | New construction, synchronous Tuyen Quang MR Plant
Ước tính khối lượng đấu nối các nguồn NLTT | 800 | 2025-2030 | New construction
Dự phòng phát sinh đường dây 220 kV cải tạo và xây mới | 314 |  | New construction
Đan Phượng 500 kV - Phúc Thọ | 2x13 | 2031-2035 | New construction
Đông Anh 2 - Rẽ Vân Trì - Tây Hồ và Vân Trì - Chèm | 4x2 | 2031-2035 | New construction
Đông Anh 3 - Rẽ Vân Trì - Đông Anh 500 kV | 4x2 | 2031-2035 | New construction
Sơn Tây 500 kV - Phúc Thọ | 2x6 | 2031-2035 | New construction
Thanh Oai - Rẽ Ứng Hòa - Hà Đông | 2x5 | 2031-2035 | New construction, connection of Thanh Oai 220kV substation
Thanh Trì - Rẽ Thường Tín - Mai Động | 2x5 | 2031-2035 | New construction, connection 220kV Thanh Tri
Vân Trì 500 kV - rẽ Vân Trì - Đông Anh 2 | 4x10 | 2031-2035 | New construction
Vân Trì 500 kV - Vân Trì 2 | 2x10 | 2031-2035 | New construction
Đấu nối TĐ Thuần Mỹ | 2x10 | 2031-2035 | New construction, synchronized power source. Specific connection plan is accurate during project implementation phase.
Đình Vũ 2 - BB2 | 2x5 | 2031-2035 | New construction
BB 2 - Cát Hải (*) | 2x5 | 2031-2035 | New construction, synchronized with the scale and progress of the offshore wind power source in the North. The detailed plan and volume will be accurate during the project implementation phase, depending on the results of the actual sea survey.
Hải Phòng 2 500 kV - Hải Phòng 2 | 2x5 | 2031-2035 | New construction
Gia Lộc 500 kV - Gia Lộc - chuyển đấu nối Gia Lộc - Tân Việt | 2x10 | 2031-2035 | New construction
Yên Mỹ - Rẽ Hưng Yên 1 500 kV - Văn Giang (mạch 2) | 2x2 | 2031-2035 | New construction
Hà Nam 500 kV - Đồng Văn | 4x12 | 2031-2035 | New construction, connection to Ha Nam 500kV
Hà Nam 500 kV - Rẽ Thanh Nghị - Lý Nhân | 4x4 | 2031-2035 | New construction, connection to Ha Nam 500kV
Kim Bảng - Rẽ Đồng Văn - Phủ Lý | 4x4 | 2031-2035 | New construction
Nam Định 2 500 kV - Rẽ Ninh Bình - Thái Bình | 2x5 | 2031-2035 | New construction
Tiền Hải - Rẽ Thái Bình - Trực Ninh | 2x2 | 2031-2035 | New construction
Thiệu Yên - Bá Thước | 2x65 | 2031-2035 | New construction
Hà Giang 2 - Hà Giang 500 kV | 2x10 | 2031-2035 | New construction
Hà Giang 500 kV - Rẽ Hà Giang - TĐ Bắc Mê và Hà Giang - Thái Nguyên | 4x10 | 2031-2035 | New construction
Quảng Uyên - Rẽ Cao Bằng - Lạng Sơn | 4x5 | 2031-2035 | New construction
Lào Cai 2 - Rẽ Lào Cai 220 kV - Trung Quốc | 2x2 | 2031-2035 | New construction
NLTT Lào Cai 3 - 500 kV Lào Cai (*) | 2x20 | 2031-2035 | New construction
Lạng Sơn 2 500 kV - Rẽ Lạng Sơn - Đồng Mỏ | 4x10 | 2031-2035 | New construction
Sơn Dương - Rẽ Tuyên Quang - Đại Từ | 2x2 | 2031-2035 | New construction
500 kV Thái Nguyên 2 - Phú Bình 3 | 2x10 | 2031-2035 | Connection to 220 kV Phu Binh 3 Substation
Phú Lương - Rẽ Thái Nguyên - TĐ Bắc Mê | 2x2 | 2031-2035 | New construction
Phúc Xuân - Rẽ Thái Nguyên 500 kV - Thái Nguyên | 2x5 | 2031-2035 | New construction
Thái Nguyên 2 500 kV - Phú Bình 2 | 2x15 | 2031-2035 | New construction
Thái Nguyên 2 500 KV- Sông Công | 2x8 | 2031-2035 | New construction
Phú Thọ 3 - Việt Trì 2 | 2x22 | 2031-2035 | New construction, connection of 220kV Viet Tri 2 substation
Phú Thọ 500 kV - Rẽ Phù Yên - Phú Thọ 2 | 2x20 | 2031-2035 | New construction
Phú Thọ 500 kV-Việt Trì 2 | 2x20 | 2031-2035 | New construction
Vĩnh Tường 500 kV - Rẽ Vĩnh Tường - Vĩnh Yên | 4x8 | 2031-2035 | New construction
Vĩnh Tường 500 kV - Vĩnh Tường | 2x8 | 2031-2035 | New construction, connection conversion to Vinh Tuong 500kV - Chan Hung
Bắc Giang 500 kV - Chũ | 2x32 | 2031-2035 | New construction
Chũ - Rẽ Sơn Động - Đồng Mỏ | 4x2 | 2031-2035 | New construction
Bắc Ninh 2 500 kV - Rẽ Bắc Ninh 4 - Bắc Ninh 7 | 4x5 | 2031-2035 | New construction
Bắc Ninh 3 500 kV - Bắc Ninh 10 | 2x12 | 2031-2035 | New construction
Bắc Ninh 3 500 kV - Bắc Ninh 9 | 4x2 | 2031-2035 | New construction
Bắc Ninh 6 - Rẽ Phả Lại - 500 kV Phố Nối (mạch 2) | 2x3 | 2031-2035 | New construction
Cộng Hòa - Vân Đồn | 2x16 | 2031-2035 | New construction and connection of 220kV Van Don substation
NLTT Lai Châu 3 - NLTT Lai Châu 1 500 kV (*) | 2x10 | 2031-2035 | New construction
NLTT Lai Châu 4 - NLTT Lai Châu 1 500 kV (*) | 2x10 | 2031-2035 | New construction
Hòa Bình 1- Yên Thủy (*) | 2x18 | 2031-2035 | New construction
Nam Hà Nội 500 kV - Lương Sơn | 2x18 | 2031-2035 | New construction
TĐ Trung Sơn MR - TĐ Trung Sơn | 1x1 | 2031-2035 | New construction, synchronized power source. Proposed plan in EVN Document No. 862/EVN-KH dated February 11, 2025. Specific connection plan is accurate during project implementation phase.
Tĩnh Gia 500 kV - chuyển đấu nối Tĩnh Gia 220 kV | 2x4 | 2031-2035 | New construction
Tĩnh Gia 500 kV - Rẽ Nông Cống - Nghi Sơn | 4x4 | 2031-2035 | New construction
Đấu nối Nam cấm 500 kV | 4x5 | 2031-2035 | Consider connecting to 220kV Nam Cam substation
Hưng Nguyên - Rẽ Đô Lương - Nam Cấm | 4x5 | 2031-2035 | New construction, connection to 220kV Hung Nguyen substation
Nam Cấm 500 kV - Cửa Lò | 2x11 | 2031-2035 | New construction
TĐ Bản Vẽ MR - TĐ Bản Vẽ | 1x1 | 2031-2035 | New construction, synchronized MR Drawing
Lộc Hà - Rẽ Hà Tĩnh - Can Lộc | 4x7 | 2031-2035 | New construction
TĐ Huội Quảng MR - TĐ Huội Quảng | 2x1 | 2031-2035 | New construction, synchronized power source. Proposed plan in document No. 15/SCT-QLNL of the Department of Industry and Trade of Tuyen Quang province dated January 3, 2025.
TĐ Huội Quảng MR - Rẽ Bản Chát - Than Uyên | 2x1 | 2031-2035 | New construction, synchronized power source. Proposed plan in document No. 15/SCT-QLNL of the Department of Industry and Trade of Tuyen Quang province dated January 3, 2025
Dự phòng phát sinh đường dây 220 kV cải tạo và xây mới | 320 | 2031-2035 | New construction and renovation

## Table 7 500 kV transformer in
Name | Capacity (MVA) | Time | Note
Quảng Bình (*) | 2700 | 2025-2030 | New construction, release of renewable energy capacity
Lao Bảo (Hướng Hóa) | 2700 | 2025-2030 | New construction, release of renewable energy capacity
Trạm cắt Quảng Trị 2 | Trạm cắt | 2025-2030 | New construction
Quảng Trị | 1800 | 2025-2030 | New construction
Đà Nẵng | 1800 | 2025-2030 | Renovation and capacity improvement
Thạnh Mỹ | 2700 | 2025-2030 | Renovation, capacity enhancement, synchronization with power source development progress
Dung Quất | 900 | 2025-2030 | New construction, the name in the list of 500kV, 220kV lines connected to Dung Quat 500 kV substation is Dung Quat substation.
Bình Định | 1800 | 2025-2030 | New construction
Kon Tum | 1800 | 2025-2030 | New construction and installation of transformer at Kon Tum 500 kV switching station in the 8th Power Development Plan, releasing renewable energy capacity
Pleiku 2 | 1800 | 2025-2030 | Renovation and capacity improvement
Pleiku 3 | 1800 | 2025-2030 | Renovation and capacity improvement
Nhơn Hòa | 1800 | 2025-2030 | New construction
Krông Buk | 1800 | 2025-2030 | New construction
Ea Nam (*) | 1800 | 2025-2030 | Renovation, capacity upgrade, and release of renewable energy capacity
Kon Rẫy (*) | 1800 | 2025-2030 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 1 (*) | 2700 | 2025-2030 | New construction, release of renewable energy capacity
Tuy Hòa | 1800 | 2025-2030 | New construction
NLTT Phú Yên 1 (*) | 1800 | 2025-2030 | New construction, release of renewable energy capacity
Dự phòng công suất TBA cho tăng trưởng phụ tải và phát triển nguồn điện | 1800 | 2025-2030 | New construction, renovation and capacity enhancement
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | New construction, including but not limited to projects: Replacement, installation of electric resistance, compensation capacitors, SVC, SVG, FACTS devices, BESS, synchronous condensers...; expansion of transformer station bays, upgrading capacity, completing transformer station diagrams in a flexible direction; installation of short-circuit current limiting devices, replacement and upgrading of devices to ensure short-circuit current tolerance, automatic circuit setup; installation, replacement of devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...
Dốc Sỏi | 1800 | 2031-2035 | Renovation and capacity improvement
Dung Quất | 1800 | 2031-2035 | Renovation, capacity increase, name in the list of 500kV, 220kV lines connected to Dung Quat 500 kV substation is Dung Quat substation.
Pleiku | 2700 | 2031-2035 | Renovation and capacity improvement
ĐMT Ea Súp | 1800 | 2031-2035 | Renovation and capacity improvement
Hương Thủy | 1800 | 2031-2035 | New construction
Hòa Liên | 900 | 2031-2035 | New construction
Mang Yang (*) | 1800 | 2031-2035 | New construction, release of renewable energy capacity
la Blứ 500 kV (*) | 900 | 2031-2035 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 1 (*) | 3600 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
Đắk Nông 2 (*) | 1800 | 2031-2035 | New construction, supply of electricity for aluminum smelting loads (as proposed in Document No. 167 UBND-KT dated January 8, 2025 of Dak Nong Provincial People's Committee) and pooling renewable energy capacity
Diên Khánh | 900 | 2031-2035 | New construction
NLTT Quảng Trị (*) | 1800 | 2031-2035 | New construction, release of renewable energy capacity
Phong Điền | 900 | 2031-2035 | New construction, considering connecting to Phong Dien 220 kV substation, releasing renewable energy capacity
NLTT Đắk Lắk 2 (*) | 3600 | 2031-2035 | New construction, release of renewable energy capacity
Dự phòng công suất TBA cho tăng trưởng phụ tải và phát triển nguồn điện | 3600 | 2031-2035 | New construction, renovation and capacity enhancement
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | New construction, including but not limited to projects: Replacement, installation of electric resistance, compensation capacitors, SVC, SVG, FACTS devices, BESS, synchronous condensers...; expansion of transformer station bays, upgrading capacity, completing transformer station diagrams in a flexible direction; installation of short-circuit current limiting devices, replacement and upgrading of devices to ensure short-circuit current tolerance, automatic circuit setup; installation, replacement of devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,.

## Table 8 500 kV lines in the Cen
Name | Number of circuits × kilometres | Time | Note
Quảng Bình - Rẽ Vũng Áng - Quảng Trị (*) | 4x5 | 2025-2030 | New construction and connection of 500 kV Quang Binh substation
NMNĐ Quảng Trị - Quảng Trị | 2x17 | 2025-2030 | New construction, in case Quang Tri Thermal Power Plant continues to be implemented
Quảng Trị - Rẽ Vũng Áng - Đà Nẵng | 4x6 | 2025-2030 | New construction and connection of 500 kV Quang Tri substation
Trạm cắt Quảng Trị 2 - Rẽ Quảng Trạch - Dốc Sỏi | 4x5 | 2025-2030 | New construction
Lao Bảo (Hướng Hóa) - Trạm cắt Quảng Trị 2 | 2x31 | 2025-2030 | New construction
Cụm NMĐ Xebanghieng (Lào) - Lao Bảo (*) | 2x20 | 2025-2030 | New construction, import electricity from Laos
LNG Hải Lăng - NMNĐ Quảng Trị | 2x6 | 2025-2030 | Newly build and synchronize Hai Lang LNG Phase 1. In case Quang Tri Thermal Power Plant is behind schedule, build first the Hai Lang - Quang Tri LNG pipeline, about 23km long, connecting Hai Lang LNG Phase 1 and Quang Tri Thermal Power Plant, transferring to Hai Lang - Quang Tri LNG pipeline (2 circuits).
Đấu nối thủy điện tích năng Trung Trung Bộ 1 (*) | 2x30 | 2025-2030 | New construction, detailed connection plan, length, cross-section and route direction of the power line will be determined accurately during the project implementation phase.
Đấu nối thủy điện tích năng Trung Trung Bộ 2 (*) | 2x30 | 2025-2030 | New construction, detailed connection plan, length, cross-section and route direction of the power line will be determined accurately during the project implementation phase.
Thạnh Mỹ - Rẽ Quảng Trạch - Dốc Sỏi | 4x45 | 2025-2030 | New construction
Monsoon - Thạnh Mỹ | 2x22 | 2025-2030 | New construction, Electricity supplied January 2025
TBKHH Dung Quất - Dốc Sỏi | 2x8 | 2025-2030 | New construction
TBKHH Miền Trung - Dốc Sỏi | 2x20 | 2025-2030 | New construction
TBKHH Dung Quất - Bình Định | 2x207 | 2025-2030 | New construction
Kon Rẫy - Rẽ Dốc Sỏi - Pleiku 2(*) | 4x5 | 2025-2030 | New construction and connection of 500 kV Kon Ray substation
Hatsan - Kon Tum (*) | 2x100 | 2025-2030 | New construction, import electricity from Laos
Kon Tum - Rẽ Thạnh Mỹ - Pleiku 2 | 4x5 | 2025-2030 | New construction and connection of 500 kV Kon Tum substation
TĐ Ialy MR - TĐ Ialy | 1x2 | 2025-2030 | New construction
Nhơn Hòa - Rẽ Pleiku - Đắk Nông | 2x4 | 2025-2030 | New construction
NLTT Đắk Lắk 1- Krông Buk (*) | 4x20 | 2025-2030 | New construction
Krong Buk - Tây Ninh 1 | 2x314 | 2025-2030 | New construction
Krông Buk - Rẽ Pleiku 2 - Chơn Thành | 4x2 | 2025-2030 | New construction and connection of 500 kV Krong Buk substation
Vân Phong - Bình Định | 2x238 | 2025-2030 | New construction
Bình Định - Krông Buk | 2x216 | 2025-2030 | New construction
NLTT Phú Yên 1 - Tuy Hòa (*) | 2x30 | 2025-2030 | New construction
Tuy Hòa - Rẽ Vân Phong - Bình Định | 4x5 | 2025-2030 | New construction and connection of 500 kV Tuy Hoa substation
Ước tính khối lượng đấu nối và giải tỏa công suất các nguồn NLTT | 200 | 2025-2030 | New construction, renovation
Dự phòng phát sinh đường dây 500 kV xây mới và cải tạo | 200 | 2025-2030 | New construction, renovation
NLTT Quảng Trị - Trạm cắt Quảng Trị 2 (*) | 2x31 | 2031-2035 | New construction
Đấu nối trạm converter HVDC Trung Trung Bộ 1 (*) | 6x20 | 2031-2035 | New construction, detailed connection plan, length, cross-section and route direction of the power line will be determined accurately during the project implementation phase.
Cải tạo Đà Nẵng - Dốc Sỏi thành 2 mạch | 2x100 | 2031-2035 | Renovation
Hương Thủy - Rẽ Quảng Trị - Đà Nẵng | 4x5 | 2031-2035 | New construction and connection of 500 kV Huong Thuy substation
Phong Điền - rẽ Hòa Liên - Trạm cắt Quảng Trị 2 | 4x10 | 2031-2035 | New construction
Hòa Liên - Rẽ Trạm cắt Quảng Trị 2 - Thạnh Mỹ | 4x5 | 2031-2035 | New construction and connection of 500 kV Hoa Lien substation
Đấu nối thủy điện tích năng Trung Trung Bộ 3 (*) | 2x30 | 2031-2035 | New construction, detailed connection plan, length, cross-section and route direction of the power line will be determined accurately during the project implementation phase.
Đấu nối trạm converter HVDC Trung Trung Bộ 2 (*) | 4x20 | 2031-2035 | New construction, detailed connection plan, length, cross-section and route direction of the power line will be determined accurately during the project implementation phase.
Đấu nối Thủy điện tích năng Trung Trung Bộ 4 (*) | 2x30 | 2031-2035 | New construction, detailed connection plan, length, cross-section and route direction of the power line will be determined accurately during the project implementation phase.
Mang Yang - Rẽ TBK Dung Quất - Krông Buk (*) | 4x5 | 2031-2035 | New construction
NLTT Đắk Lắk 1 - HVDC Trung Trung Bộ 2 (*) | 2x350 | 2031-2035 | New construction, in case of high development of renewable energy sources in the Central Highlands, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025
Ia Blứ - Rẽ Pleiku 2 - Krông Buk (*) | 2x4 | 2031-2035 | New construction
NLTT Đắk Lắk 2- rẽ Krông buk -Chơn Thành (*) | 4x30 | 2031-2035 | New construction
Đắk Nông 2 - Rẽ Krông Buk - Tây Ninh (*) | 2x30 | 2031-2035 | New construction and connection of 500 kV Dak Nong 2 substation
Cải tạo Đắk Nông - Cầu Bông 1 mạch thành 2 mạch | 2x180 | 2031-2035 | New construction, reserve for high-yield renewable energy development in the Central Highlands, based on renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025
Diên Khánh - Rẽ NĐ Vân Phong 1 - Thuận Nam | 4x5 | 2031-2035 | New construction
Cải tạo Thạnh Mỹ - Pleiku 2 thành 2 mạch | 2x199 | 2031-2035 | New construction
Ước tính khối lượng đấu nối và giải tỏa công suất các nguồn NLTT | 200 | 2031-2035 | New construction, renovation
Dự phòng phát sinh đường dây 500 kV xây mới và cải tạo | 200 | 2031-2035 | New construction, renovation

## Table 9 220 kV transformer stat
Name | Capacity (MVA) | Time | Note
Đồng Hới | 375 | 2025-2030 | Renovation and capacity improvement
Ba Đồn | 500 | 2025-2030 | Renovation and capacity improvement
Lệ Thủy (*) | 750 | 2025-2030 | New construction, release of renewable energy capacity
Lao Bảo | 750 | 2025-2030 | Renovation, capacity upgrade, and release of renewable energy capacity
Đông Hà | 500 | 2025-2030 | Renovation and capacity improvement
Hướng Linh | 250 | 2025-2030 | New construction
Hướng Tân | 500 | 2025-2030 | Renovation and capacity improvement
Đông Nam | 250 | 2025-2030 | New construction
Phong Điền | 500 | 2025-2030 | Renovation and capacity improvement
Chân Mây | 250 | 2025-2030 | New construction
Hương Thủy | 250 | 2025-2030 | New construction
Liên Chiểu | 500 | 2025-2030 | New construction
Sân Bay Đà Nẵng | 250 | 2025-2030 | New construction
Tiên Sa | 250 | 2025-2030 | New construction
Tam Kỳ | 500 | 2025-2030 | Renovation and capacity improvement
Thạnh Mỹ | 500 | 2025-2030 | Renovation and capacity improvement
Sông Tranh 2 | 500 | 2025-2030 | Renovation and capacity improvement
Duy Xuyên | 250 | 2025-2030 | Renovation and capacity improvement
Tam Hiệp | 250 | 2025-2030 | New construction
Điện Bàn | 250 | 2025-2030 | New construction
Nam Hội An | 250 | 2025-2030 | New construction
TĐ Nước Long | 275 | 2025-2030 | Renovation and capacity improvement
Dung Quất 2 | 500 | 2025-2030 | New construction
Quảng Ngãi 2 | 250 | 2025-2030 | New construction
Phước An | 500 | 2025-2030 | Renovation and capacity improvement
Phù Mỹ | 375 | 2025-2030 | Renovation and capacity improvement
Nhơn Hội | 500 | 2025-2030 | New construction
Phù Mỹ 2 | 500 | 2025-2030 | New construction, power supply for Phu My Industrial Park
Tuy Hòa | 500 | 2025-2030 | Renovation and capacity improvement
Sông Cầu | 250 | 2025-2030 | New construction
Nam Phú Yên | 750 | 2025-2030 | New construction, power supply for steel loads
Vân Phong | 500 | 2025-2030 | Renovation and capacity improvement
Vạn Ninh | 250 | 2025-2030 | New construction
Cam Thịnh | 250 | 2025-2030 | New construction
Bờ Y | 250 | 2025-2030 | New construction
Pleiku | 500 | 2025-2030 | Renovation and capacity improvement
Chư Sê | 500 | 2025-2030 | Renovation and capacity improvement
An Khê | 500 | 2025-2030 | Renovation and capacity improvement
Pleiku 2 500 kV nối cấp | 250 | 2025-2030 | New construction
Krông Pa | 250 | 2025-2030 | New construction
Gia Lai 1 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Krông Ana | 375 | 2025-2030 | Renovation and capacity improvement
Krông Buk 500 kV nối cấp | 500 | 2025-2030 | New construction
Ea Kar | 250 | 2025-2030 | New construction
Đắk Nông | 500 | 2025-2030 | Renovation and capacity improvement
Đắk Nông 2 | 500 | 2025-2030 | New construction
Điện phân nhôm | 1184 | 2025-2030 | New construction
Quảng Bình 1 (*) | 500 | 2025-2030 | New construction
Quảng Bình 2 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Quảng Trị 1 (*) | 250 | 2025-2030 | New construction, release of renewable energy capacity
Quảng Trị 2 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
NLTT Quảng Ngãi 1 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Kon Tum 1 (*) | 750 | 2025-2030 | New construction, release of renewable energy capacity
Kon Tum 2 (*) | 750 | 2025-2030 | New construction, release of renewable energy capacity
Kon Tum 3 (*) | 750 | 2025-2030 | New construction, release of renewable energy capacity
Mang Yang (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Gia Lai 2 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
NLTT Ea Hleo (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Ea Hleo | 500 | 2025-2030 | New construction
Đắk Nông 3 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Hoài Mỹ | 500 | 2025-2030 | New construction, power supply for KGN Hoai My
Phú Yên 1 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Quảng Bình 3 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 1 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 2 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 3 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Đắk Song | 500 | 2025-2030 | New construction, release of renewable energy capacity
Bình Định 1 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Phú Yên 2 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Phú Yên 3 (*) | 500 | 2025-2030 | New construction, release of renewable energy capacity
Dự phòng công suất TBA 220 kV cho tăng trưởng phụ tải và phát triển nguồn điện | 1000 | 2025-2030 | New construction, renovation and capacity enhancement
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | New construction, including but not limited to projects: Replacement, installation of electric resistance, compensation capacitors, SVC, SVG, FACTS devices, BESS, synchronous condensers...; expansion of transformer station bays, upgrading capacity, completing transformer station diagrams in a flexible direction; installation of short-circuit current limiting devices, replacement and upgrading of devices to ensure short-circuit current tolerance, automatic circuit setup; installation, replacement of devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...
Đồng Hới | 500 | 2031-2035 | Renovation and capacity improvement
Hướng Linh | 500 | 2031-2035 | Renovation and capacity improvement
Đông Nam | 500 | 2031-2035 | Renovation and capacity improvement
Hương Thủy | 500 | 2031-2035 | Renovation and capacity improvement
Hải Châu | 500 | 2031-2035 | Renovation and capacity improvement
Sân Bay Đà Nẵng | 500 | 2031-2035 | Renovation and capacity improvement
Duy Xuyên | 375 | 2031-2035 | Renovation and capacity improvement
Tam Hiệp | 500 | 2031-2035 | Renovation and capacity improvement
Dốc Sỏi | 375 | 2031-2035 | Renovation and capacity improvement
Phù Mỹ | 500 | 2031-2035 | Renovation and capacity improvement
Vạn Ninh | 500 | 2031-2035 | Renovation and capacity improvement
Cam Thịnh | 500 | 2031-2035 | Renovation and capacity improvement
Bờ Y | 500 | 2031-2035 | Renovation and capacity improvement
Gia Lai 1 (*) | 750 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
Krông Ana | 500 | 2031-2035 | Renovation and capacity improvement
Ea Kar | 500 | 2031-2035 | Renovation and capacity improvement
Quảng Trị 1 (*) | 500 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
Quảng Trị 3 (*) | 250 | 2031-2035 | New construction, release of renewable energy capacity
Quảng Trị 4 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
Mang Yang (*) | 750 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
Gia Lai 2 (*) | 750 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
ĐGNK Trung Trung Bộ | 500 | 2031-2035 | New construction
NLTT Huế 1 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
NLTT Huế 2 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
Kon Tum 4 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
Kon Tum 5 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
Gia Lai 3 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
Gia Lai 4 (*) | 500 | 2031-2035 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 1 (*) | 750 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
NLTT Đắk Lắk 2 (*) | 750 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
NLTT Đắk Lắk 3 (*) | 750 | 2031-2035 | Renovation, capacity upgrade, and release of renewable energy capacity
NLTT Đắk Lắk 4 (*) | 750 | 2031-2035 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 5 (*) | 750 | 2031-2035 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 6 (*) | 750 | 2031-2035 | New construction, release of renewable energy capacity
NLTT Đắk Lắk 7 (*) | 750 | 2031-2035 | New construction, release of renewable energy capacity
Đắk Nông 4 (*) | 750 | 2031-2035 | New construction, release of renewable energy capacity
Dự phòng công suất TBA 220 kV cho tăng trưởng phụ tải và phát triển nguồn điện | 2000 | 2031-2035 | New construction, renovation and capacity enhancement
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | New construction, including but not limited to projects: Replacement, installation of electric resistance, compensation capacitors, SVC, SVG, FACTS devices, BESS, synchronous condensers...; expansion of transformer station bays, upgrading capacity, completing transformer station diagrams in a flexible direction; installation of short-circuit current limiting devices, replacement and upgrading of devices to ensure short-circuit current tolerance, automatic circuit setup; installation, replacement of devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...

## Table 10 220 kV lines in the C
Name | Number of circuits × kilometres | Time | Note
Ba Đồn - Rẽ Vũng Áng - Đồng Hới | 2x3 | 2025-2030 | New construction, circuit 2 forwarding
Lệ Thủy - Rẽ Đồng Hới - Đông Hà | 4x2 | 2025-2030 | New construction, connection to 220 kv Le Thuy substation
Điện gió B&T1 - Rẽ Đồng Hới - Đông Hà mạch 2 | 4x10 | 2025-2030 | New construction
Quảng Bình 500 kV - Rẽ Đồng Hới - Đông Hà | 4x5 | 2025-2030 | New construction and connection of 500 kV Quang Binh substation
Nâng khả năng tải Đồng Hới - Đông Hà | 2x108 | 2025-2030 | Renovation
Quảng Bình 1 - Quảng Bình 500 kV(*) | 2x21 | 2025-2030 | New construction
Quảng Bình 2 - Quảng Bình 500 kV (*) | 2x25 | 2025-2030 | New construction
Quảng Bình 3 - Quảng Bình 500 kV (*) | 2x25 | 2025-2030 | New construction
TBA 500 kV Quảng Trị rẽ Đông Hà - Huế và Đông Hà - Phong Điền | 6x6 | 2025-2030 | New construction and connection of 500 kV Quang Tri substation
Quảng Trị 500 kV - Đông Nam | 2x27 | 2025-2030 | New construction, connection to 220 kV Southeast Substation
Đông Hà - Huế mạch 3 | 1x78 | 2025-2030 | Renovation, Dong Ha - Quang Tri 500 kV - Hue
ĐG TNC Quảng Trị 1 - Hướng Tân | 1x11 | 2025-2030 | New construction, release of renewable energy sources
Hướng Linh - Lao Bảo | 1x12 | 2025-2030 | New construction, release of renewable energy sources
ĐG LIG Hướng Hóa 1 - Hướng Tân | 1x13 | 2025-2030 | New construction, release of renewable energy sources
ĐG LIG Hướng Hóa 2 - LIG Hướng Hóa 1 | 1x8 | 2025-2030 | New construction, release of renewable energy sources
ĐG Savan 1 - Lao Bảo | 2x17 | 2025-2030 | New construction, when Lao Bao 500 kV substation comes into operation, transfer connection to Lao Bao 500 kV substation (Huong Hoa)
500 kV Lao Bảo (Hướng Hóa) - Rẽ Lao Bảo - Đông Hà | 4x5 | 2025-2030 | New construction and connection of 500 kV Lao Bao substation (Huong Hoa)
500 kV Lao Bảo (Hướng Hóa) - Rẽ ĐG Tài Tâm - Lao Bảo | 2x5 | 2025-2030 | New construction and connection of 500 kV Lao Bao substation (Huong Hoa)
Quảng Trị 1 - Quảng Trị 500 kV (*) | 2x10 | 2025-2030 | New construction
Quảng Trị 2 - Lao Bảo 500 kV (*) | 2x10 | 2025-2030 | New construction
Chân Mây - Rẽ Hòa Khánh - Huế | 4x5 | 2025-2030 | New construction and connection of 220 kV Chan May substation
Phong Điền - Rẽ Đông Hà - Huế (mạch 2) | 2x5 | 2025-2030 | New construction
Hương Thủy - Rẽ Huế - Hòa Khánh | 4x2 | 2025-2030 | New construction and connection of 220 kV Huong Thuy substation
Nâng khả năng tải Huế - Hòa Khánh | 2x82 | 2025-2030 | Renovation
Nâng khả năng tải Đà Nẵng - Tam Kỳ - Dốc Sỏi | 2x100 | 2025-2030 | Renovation
Liên Chiểu - Rẽ Hòa Khánh - Huế | 4x3 | 2025-2030 | New construction, connection to 220 kV Lien Chieu substation
Hải Châu - Ngũ Hành Sơn | 2x11 | 2025-2030 | New construction
Tiên Sa - Rẽ Hải Châu - Ngũ Hành Sơn | 2x3 | 2025-2030 | New construction, connection to 220 kV Tien Sa substation
Sân bay Đà Nẵng - rẽ Hòa Khánh - Đà Nẵng | 2x5 | 2025-2030 | New construction, connection of 220 kV substation at Da Nang Airport
Điện Bàn - Nam Hội An | 2x24 | 2025-2030 | New construction
Tam Hiệp - Rẽ Tam Kỳ - Dốc Sỏi | 4x1 | 2025-2030 | New construction, connection to Tam Hiep 220 kV substation
Đà Nẵng 500 kV - Điện Bàn | 2x12 | 2025-2030 | New construction, connection of 220 kV Dien Ban substation
TĐ Nam Emoun - Trạm cắt Đắk Ooc | 1x51 | 2025-2030 | New construction
Nâng khả năng tải Đắk Ooc - Thạnh Mỹ | 2x31 | 2025-2030 | Improving and increasing Laos' electricity imports
Thạnh Mỹ - Duy Xuyên | 2x69 | 2025-2030 | New construction, 500 kV Thanh My - Duy Xuyen substation
Trạm cắt 220 kV Đắk Ooc - TĐ Sông Bung 2 | 2x10 | 2025-2030 | New construction, increased import of electricity from Laos
Phước An - Rẽ TĐ An Khê - Quy Nhơn (mạch 1) | 2x2 | 2025-2030 | Renovation
TBKHH Dung Quất - Dung Quất 2 | 2x6 | 2025-2030 | New construction and connection of Dung Quat 2 220 kV substation
Dung Quất - Dung Quất 2 | 2x3 | 2025-2030 | New construction
Nâng khả năng tải Dốc Sỏi - Dung Quất | 2x8 | 2025-2030 | Renovation and consideration of new construction plan for Doc Soi - Dung Quat Science and Technology Center section
TBKHH Dung Quất - Rẽ Dốc Sỏi - Dung Quất | 4x3 | 2025-2030 | New construction, adjusting the scale to 2x3 in case of new construction of Doc Soi - Dung Quat Industrial Park section
Quảng Ngãi 2 - Rẽ Dốc Sỏi - Quảng Ngãi | 4x2 | 2025-2030 | New construction
NLTT Quảng Ngãi 1 - rẽ Quảng Ngãi - Phù Mỹ (*) | 4x2 | 2025-2030 | New construction
Nâng khả năng tải Sơn Hà - Dốc Sỏi | 2x46 | 2025-2030 | Renovation
Nâng khả năng tải Quảng Ngãi - Dốc Sỏi | 2x60 | 2025-2030 | Renovation
Thay dây phân pha mạch 1 đường dây Quảng Ngãi - Quy Nhơn (Phước An) | 1x140 | 2025-2030 | Renovation
Trạm cắt 220 kV Bờ Y - Bờ Y | 2x30 | 2025-2030 | New construction
Bờ Y - Kon Tum | 2x51 | 2025-2030 | New construction
TĐ Đắk Mi 1 - TĐ Đắk My 2 | 1x15 | 2025-2030 | New construction
TĐ Đắk Lô 3 - Rẽ Thượng Kon Tum - Quảng Ngãi | 4x1 | 2025-2030 | New construction
Kon Rẫy 500 kV - Rẽ Thượng Kon Tum - Kon Tum | 4x5 | 2025-2030 | New construction and connection of 500 kV Kon Ray substation
Thượng Kon Tum - Kon Tum | 2x82 | 2025-2030 | New construction
Nâng khả năng tải Kon Tum - Pleiku | 2x36 | 2025-2030 | Renovation
Kon Tum 500 kV- rẽ Bờ Y- Kon Tum (*) | 4x5 | 2025-2030 | New construction
Kon Tum 1 - Kon Tum 500 kV (*) | 2x26 | 2025-2030 | New construction
Kon Tum 2 - Kon Rẫy 500 kV (*) | 2x30 | 2025-2030 | New construction
Kon Tum 3 - 500 kV Kon Rẫy (*) | 2x30 | 2025-2030 | New construction
Sơn Hà - Thượng Kon Tum | 2x35 | 2025-2030 | New construction
Nâng khả năng tải Pleiku - ĐSK An Khê - TĐ An Khê | 1x98 | 2025-2030 | Renovation
Chư Sê - Rẽ Pleiku 2 - Krông Buk (mạch 2) | 2x2 | 2025-2030 | New construction
Pleiku 2 - Krông Buk Mạch 2 | 1x120 | 2025-2030 | Renovation
Krông Pa - Chư Sê | 2x63 | 2025-2030 | New construction
ĐG Ia Le 1 - Rẽ Krông Buk - Pleiku 2 (mạch 2) | 2x6 | 2025-2030 | New construction
ĐG la Boòng - Chư Prông - ĐG Nhơn Hòa 1 | 1x8 | 2025-2030 | New construction
Mang Yang - Rẽ TĐ An Khê - Pleiku (*) | 2x5 | 2025-2030 | New construction
Gia Lai 1 - Pleiku 3 (*) | 2x20 | 2025-2030 | New construction
Gia Lai 2 - Nhơn Hòa (*) | 2x20 | 2025-2030 | New construction
Krông Buk 500 kV - Krong Buk | 2x27 | 2025-2030 | New construction
Krông Buk - Nha Trang Mạch 2 | 1x150 | 2025-2030 | Renovation
Ea Kar - Rẽ Krông Buk - Nha Trang | 4x2 | 2025-2030 | New construction
Nâng khả năng tải TĐ Srepok 3 - Buôn Kuop | 1x34 | 2025-2030 | Renovation
NLTT Ea Hleo - 500 kV Ea Nam (*) | 1x12 | 2025-2030 | New construction
Ea Hleo - Rẽ Krong Buk - Chư Sê | 4x5 | 2025-2030 | New construction
TĐ Sông Ba Hạ - Krong Buk 500 kV | 2x115 | 2025-2030 | New construction
ĐG Krông Buk - Rẽ Krông Buk - Pleiku 2 mạch 2 | 2x1 | 2025-2030 | New construction
NLTT Đắk Lắk 1 - NLTT Đắk Lắk 1 500 kV (*) | 2x20 | 2025-2030 | New construction
NLTT Đắk Lắk 2 - NLTT Đắk Lắk 1 500 kV (*) | 2x20 | 2025-2030 | New construction
NLTT Đắk Lắk 3 - NLTT Đắk Lắk 1 500 kV (*) | 2x20 | 2025-2030 | New construction
Nâng khả năng tải Buôn Kuop - Buôn Tua Shra - Đắk Nông 500 kV | 1x112 | 2025-2030 | Renovation
Đắk Nông 2 - Rẽ Buôn Kuốp - Buôn Tua Srah | 2x10 | 2025-2030 | New construction
Đắk Nông 3 - Đắk Nông 500 kV | 1x12 | 2025-2030 | New construction
Đắk Song - rẽ Đắk Nông - Buôn Kuop | 2x4 | 2025-2030 | New construction
Nâng khả năng tải Pleiku 2 - Phước An | 1x98 | 2025-2030 | New construction
Phước An - Nhơn Hội | 2x22 | 2025-2030 | New construction
Bình Định 500 kV - Rẽ Phước An - Phù Mỹ | 4x5 | 2025-2030 | New construction
Bình Định 500 kV - Rẽ An Khê - Quy Nhơn và Pleiku 2 - Phước An | 4x35 | 2025-2030 | New construction
Phù Mỹ 2 - Phù Mỹ | 2x20 | 2025-2030 | New construction
Phù Mỹ - Rẽ Phước An - Quảng Ngãi (mạch 2) | 2x2 | 2025-2030 | Renovation
Hoài Mỹ - rẽ Phù Mỹ - Quảng Ngãi | 4x5 | 2025-2030 | New construction
Bình Định 1 - Bình Định 500 kV (*) | 2x20 | 2025-2030 | New construction
Nâng khả năng tải Tuy Hòa - Vân Phong - Nha Trang | 2x118 | 2025-2030 | Renovation
Tuy Hòa - Phước An | 2x93 | 2025-2030 | New construction
HBRE An Thọ - Tuy Hòa | 1x16 | 2025-2030 | New construction
Nâng khả năng tải Tuy Hòa - Quy Nhơn | 1x90 | 2025-2030 | Renovation
Đấu nối TBA 220 kV Sông Cầu | 4x5 | 2025-2030 | New construction, Phase 1: Transition connection on the existing Tuy Hoa - Quy Nhon 220 kV line. Phase 2: Switch to transition connection on 02 circuits of Tuy Hoa - Phuoc An 220 kV line after this line is put into operation.
Nam Phú Yên - Rẽ Nha Trang - Tuy Hòa | 4x4 | 2025-2030 | New construction, steel load power supply
Phú Yên 1- Tuy Hòa 500kV (*) | 2x21 | 2025-2030 | New construction
Tuy Hòa 500 kV - Rẽ Tuy Hòa - Phước An | 4x5 | 2025-2030 | New construction and connection of 500 kV Tuy Hoa substation
Phú Yên 2 - NLTT Phú Yên 1 500 kV (*) | 2x21 | 2025-2030 | New construction
Phú Yên 3 - NLTT Phú Yên 1 500 kV (*) | 2x21 | 2025-2030 | New construction
Vạn Ninh - Rẽ Vân Phong - Tuy Hòa | 4x2 | 2025-2030 | New construction
500 kV Vân Phong - Rẽ Tuy Hòa - Vân Phong 220 kV (mạch 2) | 2x26 | 2025-2030 | New construction
Cam Thịnh - Rẽ Cam Ranh - Tháp Chàm | 4x3 | 2025-2030 | New construction
Vân Phong 500 kV - Vân Phong 220 kV | 2x20 | 2025-2030 | New construction
TĐ Sê San 3 MR - rẽ Sê San 3 A - Sê San 3 | 2x2 | 2025-2030 | New construction and connection of Se San 3 MR Power Plant as proposed in EVN's Official Dispatch No. 862/EVN-KH dated February 11, 2025. The specific connection plan will be finalized during the project implementation phase.
TĐ Sê San 4 MR - rẽ Pleiku - Sê San 4 | 2x1 | 2025-2030 | New construction and connection of Se San 4 MR Power Plant as proposed in EVN's Official Dispatch No. 862/EVN-KH dated February 11, 2025. The specific connection plan will be finalized during the project implementation phase.
TĐ Srêpốk 3 MR - rẽ TĐ Srêpốk 3 - Buôn Kuốp | 2x1 | 2025-2030 | New construction and connection of Srepok 3 MR Power Plant as proposed in EVN's Official Dispatch No. 862/EVN-KH dated February 11, 2025. The specific connection plan will be finalized during the project implementation phase.
TĐ Buôn Kuốp MR - rẽ Buôn Kuốp - Krông Ana | 2x1 | 2025-2030 | New construction and connection of Buôn Kuốp MR Power Plant as proposed in EVN's Official Dispatch No. 862/EVN-KH dated February 11, 2025. The specific connection plan will be finalized during the project implementation phase.
ĐG Đắk ND’rung 1,2,3 - Đắk Nông 500 kV | 2x18 | 2025-2030 | The project is included in Decision No. 500/QD-TTg dated March 15, 2023. Newly and synchronously construct Dak ND'rung 1,2,3 power plants in case these power plants are eligible for implementation.
Ước tính khối lượng đấu nối và giải tỏa công suất các nguồn NLTT | 500 | 2025-2030 | New construction, renovation
Dự phòng phát sinh đường dây 220 kV xây mới và cải tạo | 500 | 2025-2030 | New construction, renovation
TBKHH Quảng Trị - Rẽ Đông Nam - 500 kV Quảng Trị | 2x5 | 2031-2035 | New construction
Quảng Trị 3 - NLTT Quảng Trị 500 kV (*) | 2x16 | 2031-2035 | New construction
Quảng Trị 4 - NLTT Quảng Trị 500 kV (*) | 2x20 | 2031-2035 | New construction
Hương Thủy - Huế - chuyển đấu nối Phong Điền | 2x19 | 2031-2035 | New construction
Phong Điền 500 kV - rẽ Phong Điền - Huế | 4x2 | 2031-2035 | New construction
NLTT Huế 1 - Phong Điền 500 kV (*) | 2x20 | 2031-2035 | New construction
NLTT Huế 2 - Phong Điền 500 kV (*) | 2x20 | 2031-2035 | New construction
Đà Nẵng 500 kV - rẽ Ngũ Hành Sơn - Duy Xuyên | 2x8 | 2031-2035 | New construction
Hòa Khánh - Rẽ Hải Châu - Đà Nẵng | 2x1 | 2031-2035 | New construction
500 kV Hòa Liên - Hòa Khánh - chuyển đấu nối Liên Chiểu | 2x6 | 2031-2035 | New construction
500 kV Hòa Liên - Rẽ Hòa Khánh - Hải Châu | 4x6 | 2031-2035 | New construction and connection of 500 kV Hoa Lien substation
TĐ Sông Tranh 2 MR - TĐ Sông Tranh 2 | 1x1 | 2031-2035 | New construction
Cải tạo nâng khả năng tải Duy Xuyên - Đà Nẵng | 1x30 | 2031-2035 | Renovation
Cải tạo nâng khả năng tải Duy Xuyên - Ngũ Hành Sơn - Đà Nẵng | 1x50 | 2031-2035 | Renovation
Cải tạo nâng khả năng tải Thạnh Mỹ 500 kV - Thạnh Mỹ | 2x20 | 2031-2035 | Renovation
Kon Tum 4 - Kon Tum 500 kV (*) | 2x30 | 2031-2035 | New construction
Kon Tum 5 - Kon Rẫy 500 kV (*) | 2x30 | 2031-2035 | New construction
Mang Yang 500 kV - rẽ An Khê - Pleiku 2 (*) | 2x10 | 2031-2035 | New construction
Mang Yang 500 kV - rẽ TĐ An Khê - Pleiku (*) | 2x10 | 2031-2035 | New construction
Ia Blứ 500 kV - rẽ Chư Sê - Krông Buk (*) | 4x20 | 2031-2035 | New construction
Gia Lai 3 - Mang Yang 500 kV (*) | 2x20 | 2031-2035 | New construction
Gia Lai 4 - Mang Yang 500 kV (*) | 2x20 | 2031-2035 | New construction
NLTT Đắk Lắk 4 - ĐMT Easup (*) | 2x20 | 2031-2035 | New construction
NLTT Đắk Lắk 5 - NLTT Đắk Lắk 2 500 kV (*) | 2x20 | 2031-2035 | New construction
NLTT Đắk Lắk 6 - NLTT Đắk Lắk 2 500 kV (*) | 2x20 | 2031-2035 | New construction
NLTT Đắk Lắk 7 - NLTT Đắk Lắk 2 500 kV (*) | 2x20 | 2031-2035 | New construction
Đắk Nông 4 - Đắk Nông 2 500 kV (*) | 2x12 | 2031-2035 | New construction
Diên Khánh - Rẽ Nha Trang - Cam Ranh | 4x7 | 2031-2035 | New construction and connection of 500 kV Dien Khanh substation
Đấu nối TĐ Sông Tranh MR | 2x5 | 2031-2035 | New construction and connection of Song Tranh MR Hydropower Plant as proposed in EVN's Official Dispatch No. 862/EVN-KH dated February 11, 2025. The specific connection plan will be finalized during the project implementation phase.
TĐ Sê San 3A MR - rẽ TĐ Sê San 3 - TĐ Sê San 3A | 2x2 | 2031-2035 | New construction and connection of Se San 3A MR Power Plant as proposed in Document No. 11/BC-UBND of Kon Tum Provincial People's Committee dated January 13, 2025. The specific connection plan will be finalized during the project implementation phase.
Ước tính khối lượng đấu nối và giải tỏa công suất các nguồn NLTT | 500 | 2031-2035 | New construction, renovation
Dự phòng phát sinh đường dây 220 kV xây mới và cải tạo | 500 | 2031-2035 | New construction, renovation

## Table 11 500kv transformer sout
Name | Capacity (MVA) | Time | Note
Di Linh | 1800 | 2025-2030 | Renovation and capacity improvement
Thuận Nam | 2700 | 2025-2030 | Renovation and capacity improvement
Ninh Sơn | 2700 | 2025-2030 | New construction, flexible operating diagram design
Sơn Mỹ | 900 | 2025-2030 | New construction
Hồng Phong (*) | 1800 | 2025-2030 | New construction, renewable energy release
NTB 1 (*) | 2700 | 2025-2030 | New construction, synchronized with scale and progress of offshore wind power source in South Central Vietnam
Cầu Bông | 2700 | 2025-2030 | Renovation and capacity improvement
Củ Chi | 1800 | 2025-2030 | New construction
Chơn Thành | 1800 | 2025-2030 | Renovation and capacity improvement
Tây Ninh 1 | 1800 | 2025-2030 | New construction
Tây Ninh 2 | 900 | 2025-2030 | New construction
Tân Định | 2700 | 2025-2030 | Renovation and capacity improvement
Tân Uyên | 2700 | 2025-2030 | Renovation and capacity improvement
Bình Dương 1 | 1800 | 2025-2030 | New construction
Bình Dương 2 | Trạm cắt | 2025-2030 | New construction and backup connection of South Central - South inter-regional transmission lines
Sông Mây | 2700 | 2025-2030 | Renovation and capacity improvement
Long Thành | 1800 | 2025-2030 | Renovation and capacity improvement
Đồng Nai 2 | 1800 | 2025-2030 | New construction
Phú Mỹ | 900 | 2025-2030 | Renovation and capacity improvement
Bắc Châu Đức | 1800 | 2025-2030 | New construction
Đức Hòa | 1800 | 2025-2030 | Renovation and capacity improvement
Long An | 1800 | 2025-2030 | New construction
Bến Tre (*) | 900 | 2025-2030 | New construction, renewable energy release
Thốt Nốt | 1800 | 2025-2030 | New construction
Duyên Hải | 1350 | 2025-2030 | Renovation and capacity improvement
Trà Vinh 1 (*) | 1800 | 2025-2030 | New construction, in case of high development of renewable energy sources in Tra Vinh province, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025
Long Phú | 1800 | 2025-2030 | Renovation and capacity improvement
Sóc Trăng (*) | 1800 | 2025-2030 | New construction, renewable energy release
Bạc Liêu (*) | 1800 | 2025-2030 | New construction, renewable energy release
Cà Mau (*) | 1800 | 2025-2030 | New construction, renewable energy release
Công suất dự phòng TBA cho tăng trường phụ tải và phát triển nguồn miền Nam | 3600 | 2025-2030 | Provision for new 500 kV substation construction and capacity upgrade
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | Including but not limited to projects: Replacing, installing electric resistors, capacitor banks, SVCs, SVGs, FACTS devices, BESSs, synchronous compensators...; expanding transformer station bays, renovating and completing transformer station diagrams in a flexible direction; installing short-circuit current limiting devices, replacing and upgrading devices to ensure short-circuit current tolerance, setting up automatic circuits; replacing devices to ensure synchronous load capacity of lines and transformers; installing, replacing devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...
Lâm Đồng | 1800 | 2031-2035 | New construction, synchronized aluminum smelting load (according to the request in Document No. 23/SCT-QLNL dated January 4, 2025 of the Department of Industry and Trade of Lam Dong province)
500 kV Ninh Thuận 1 (*) | 1800 | 2031-2035 | New construction, renewable energy release
500 kV Ninh Thuận 2 (*) | 1800 | 2031-2035 | New construction, renewable energy release
Hồng Phong (*) | 2700 | 2031-2035 | Renovation and capacity improvement
NTB 2 (*) | 1800 | 2031-2035 | New construction, synchronized with scale and progress of offshore wind power source in South Central Vietnam
NTB 3 (*) | 1800 | 2031-2035 | New construction, synchronized with scale and progress of offshore wind power source in South Central Vietnam
Củ Chi | 2700 | 2031-2035 | Renovation and capacity improvement
Đa Phước | 2700 | 2031-2035 | New construction, flexible operating diagram design
TP Thủ Đức | 1800 | 2031-2035 | New construction
Chơn Thành | 2700 | 2031-2035 | Renovation and capacity improvement
Lộc Ninh (*) | 2700 | 2031-2035 | New construction, renewable energy release
Tây Ninh 2 | 1800 | 2031-2035 | Renovation and capacity improvement
Tây Ninh 3 (*) | 900 | 2031-2035 | New construction, renewable energy release
Bình Dương 1 | 2700 | 2031-2035 | Renovation and capacity improvement
Bình Dương 2 | 2700 | 2031-2035 | Installing transformer at 500 kV Binh Duong 2 Switching Station
Long Thành | 2700 | 2031-2035 | Renovation and capacity improvement
Đồng Nai 4 (*) | 2700 | 2031-2035 | New construction, renewable energy release
Long Điền | 1800 | 2031-2035 | New construction
Long An 2 | 900 | 2031-2035 | New construction
Đồng Tháp | 1800 | 2031-2035 | New construction
An Giang | 1800 | 2031-2035 | New construction
Tiền Giang | 1800 | 2031-2035 | New construction
Bến Tre (*) | 1800 | 2031-2035 | Renovation and capacity improvement
Thốt Nốt | 2700 | 2031-2035 | Renovation and capacity improvement
Duyên Hải | 1800 | 2031-2035 | Renovation and capacity improvement
Trà Vinh 2 (*) | 900 | 2031-2035 | New construction, renewable energy release
Công suất dự phòng TBA cho tăng trưởng phụ tải và phát triển nguồn miền Nam | 3600 | 2031-2035 | Provision for new 500 kV substation construction and capacity upgrade
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | Including but not limited to projects: Replacing, installing electric resistors, capacitor banks, SVCs, SVGs, FACTS devices, BESSs, synchronous compensators...; expanding transformer station bays, renovating and completing transformer station diagrams in a flexible direction; installing short-circuit current limiting devices, replacing and upgrading devices to ensure short-circuit current tolerance, setting up automatic circuits; replacing devices to ensure synchronous load capacity of lines and transformers; installing, replacing devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...

## Table 12 500kv lines southern
Name | Number of circuits × kilometres | Time | Note
Ninh Sơn - Rẽ NMNĐ Vân Phong I - Thuận Nam | 4x18 | 2025-2030 | New construction and connection of 500 kV Ninh Son substation
Ninh Sơn - Chơn Thành | 2x275 | 2025-2030 | New construction, release of power source capacity. Replace the 500 kV Thuan Nam - Chon Thanh transmission line approved in Document No. 1891/TTg-CN dated December 27, 2018 to facilitate investment, construction, management and operation.
TĐTN Bác Ái - Ninh Sơn | 2x25 | 2025-2030 | New and synchronous construction of Bac Ai TDT, replacing the 500 kV Bac Ai TDT - Van Phong branch - Thuan Nam
TĐTN Phước Hòa - Ninh Sơn | 2x25 | 2025-2030 | New construction, synchronized Phuoc Hoa Youth Union
Hồng Phong - Rẽ Vĩnh Tân - Sông Mây | 4x10 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
Sơn Mỹ - Bắc Châu Đức | 2x80 | 2025-2030 | New and synchronized construction of Son My II Thermal Power Plant
NMNĐ Vĩnh Tân III - Vĩnh Tân | 2x1 | 2025-2030 | New and synchronous construction of Vinh Tan III Thermal Power Plant
LNG Cà Ná - Thuận Nam | 2x30 | 2025-2030 | New construction, synchronized LNG Ca Na
Đấu nối Điện hạt nhân Ninh Thuận 1 (giải tỏa công suất về Nam Bộ) | 2x300 | 2025-2030 | Newly build and synchronize Ninh Thuan 1 Nuclear Power Plant. Consider connecting to Binh Duong 1 500kV substation. In case of high power development in the South Central region, consider developing a transmission grid with a voltage level of 765÷1000 kV.
Đấu nối Điện hạt nhân Ninh Thuận 1 | 4x15 | 2025-2030 | New construction, synchronization of Ninh Thuan 1 Nuclear Power Plant. Consider transition connection on 500kV Thuan Nam - Vinh Tan line.
Đấu nối Điện hạt nhân Ninh Thuận 2 | 2x60 | 2025-2030 | New construction, synchronization of Ninh Thuan 2 Nuclear Power Plant. Consider connection to Ninh Son 500kV Substation
Đấu nối Điện hạt nhân Ninh Thuận 2 (giải tỏa công suất về Nam Bộ) | 2x325 | 2025-2030 | Newly build and synchronize Ninh Thuan 2 Nuclear Power Plant. Consider connecting to Binh Duong 2 500kV Station. In case of high power development in the South Central region, consider developing a transmission grid with a voltage level of 765÷1000 kV.
NTB 1 - Hồng Phong (*) | 2x20 | 2025-2030 | New construction, synchronized with the scale and progress of offshore wind power sources in the South Central region. The length, cross-section and direction of the line will be precisely determined during the project implementation phase, depending on the results of the actual sea survey.
Tây Ninh 1 - Rẽ Chơn Thành - Đức Hòa | 4x2 | 2025-2030 | New construction and connection of 500 kV Tay Ninh 1 substation
Tây Ninh 2 - Rẽ Chơn Thành - Tây Ninh 1 | 2x30 | 2025-2030 | New construction and connection of 500 kV Tay Ninh 2 substation
Bắc Châu Đức - Rẽ Phú Mỹ - Sông Mây và Phú Mỹ - Long Thành | 4x11 | 2025-2030 | New construction and connection of 500 kV Bac Chau Duc substation
Nâng khả năng tải ĐD 500 kV Bắc Châu Đức - Sông Mây | 1x58 | 2025-2030 | Improve and enhance the ability to release regional power source capacity
Nâng khả năng tải ĐD 500 kV Bắc Châu Đức - Long Thành - Sông Mây | 1x92 | 2025-2030 | Improve and enhance the ability to release regional power source capacity
Nâng khả năng tải ĐD 500 kV Phú Mỹ - Nhà Bè và Phú Mỹ - NMĐ Nhơn Trạch 4 - Nhà Bè | 2x43 | 2025-2030 | Improve and enhance the ability to release regional power source capacity
Củ Chi - Rẽ Chơn Thành - Đức Hòa | 2x16 | 2025-2030 | New construction and connection of 500 kV Cu Chi substation
Bình Dương 1 - Rẽ Sông Mây - Tân Định | 2x35 | 2025-2030 | New construction and connection of 500 kV Binh Duong 1 substation
Bình Dương 1 - Chơn Thành | 2x17 | 2025-2030 | Build new, create loop circuit to improve regional power supply reliability
Bình Dương 2 - Rẽ Tây Ninh 1 - Chơn Thành | 4x5 | 2025-2030 | New construction and connection of 500 kV Binh Duong 2 switching station
Đồng Nai 2 - Rẽ Vĩnh Tân - Sông Mây | 4x5 | 2025-2030 | New construction, transition on circuit 3,4 500 kV Vinh Tan - Song May branch - Tan Uyen line
NMĐ Nhơn Trạch 4 - Rẽ Phú Mỹ - Nhà Bè | 2x4 | 2025-2030 | New and synchronous construction of Nhon Trach 4 Power Plant
Long Thành - Rẽ Bắc Châu Đức - Sông Mây | 2x17 | 2025-2030 | New construction, strengthening regional power transmission. Proposal to select appropriate cross-section for the 500 kV Bac Chau Duc - Song May transmission line after renovation to increase load capacity.
Đức Hòa - Chơn Thành | 2x104 | 2025-2030 | New construction, transfer of connection My Tho - Chon Thanh
500 kV Đức Hòa - Rẽ Phú Lâm - Cầu Bông (mạch 2) | 2x13 | 2025-2030 | New construction, connection of Duc Hoa 500 kV station to relay on the remaining circuit of Phu Lam - Cau Bong 500 kV line
Long An - Rẽ Nhà Bè - Mỹ Tho | 2x1 | 2025-2030 | New construction, connection of 500 kV Long An substation
Nâng khả năng tải ĐD 500 kV Đức Hòa - Cầu Bông | 2x24 | 2025-2030 | Upgrading to increase loading capacity, releasing capacity of LNG Bac Lieu and renewable energy sources in the Southwest
500 kV Trà Vinh 1 - Sông Hậu (*) | 2x65 | 2025-2030 | New construction, in case of high development of renewable energy sources in Tra Vinh province, on the basis of renewable energy sources allocated to localities according to Document No. 1649/BCT-DL of the Ministry of Industry and Trade dated March 5, 2025
500 kV Bến Tre - Long An (*) | 2x55 | 2025-2030 | New construction, connection to Ben Tre 500 kV substation, transfer connection to Da Phuoc 500 kV substation in the period 2031-2035
Ô Môn - Thốt Nốt | 2x35 | 2025-2030 | Build new and strengthen the transmission grid in the Southwest region; relieve capacity of O Mon Power Center
NMNĐ Sông Hậu II - Sông Hậu | 2x1 | 2025-2030 | New and synchronous construction of Song Hau II Thermal Power Plant
Thốt Nốt - Đức Hòa | 2x135 | 2025-2030 | New construction, release of LNG Bac Lieu capacity and renewable energy sources in the Southwest, consider switching the connection to Cau Bong to limit short circuit current
LNG Bạc Liêu - Thốt Nốt | 2x130 | 2025-2030 | New construction, synchronous LNG Bac Lieu
500 kV Bạc Liêu - Rẽ LNG Bạc Liêu - Thốt Nốt (*) | 2x20 | 2025-2030 | New construction, release of renewable energy sources
500 kV Cà Mau - 500 kV Bạc Liêu (*) | 2x67 | 2025-2030 | New construction, renewable energy release
500 kV Sóc Trăng - Long Phú (*) | 2x40 | 2025-2030 | New construction, renewable energy release
Dự phòng phát sinh đường dây 500 kV cải tạo và xây mới | 450 | 2025-2030 | Provision for load growth and power source development
500 kV Ninh Thuận 1 - Rẽ Vân Phong - Ninh Sơn (*) | 2x50 | 2031-2035 | New construction, synchronized with the scale and progress of regional power sources
500 kV Ninh Thuận 2 - Rẽ Thuận Nam - Ninh Sơn (*) | 2x50 | 2031-2035 | New construction, synchronized with the scale and progress of regional power sources. Consider transferring the connection to the South Central Coast HVDC Converter Station when the South Central Coast - North Coast HVDC transmission system appears.
Đấu nối trạm Converter HVDC Nam Trung Bộ | 160 | 2031-2035 | New construction, connection of HVDC converter station in South Central Coast, consideration of connection to Ninh Thuan 1 and Ninh Thuan 2 power plants
TĐTN Đơn Dương - Rẽ Điện hạt nhân Ninh Thuận 2 - Bình Dương 2 | 4x20 | 2031-2035 | New construction, synchronized with Don Duong Industrial Zone
Hồng Phong - Long Thành (*) | 2x130 | 2031-2035 | New construction, synchronized with the scale and progress of regional power sources
NTB 2 - Rẽ Hồng Phong - Long Thành (*) | 4x25 | 2031-2035 | New construction, synchronized with the scale and progress of offshore wind power sources in the South Central region. The length, cross-section and direction of the line will be precisely determined during the project implementation phase, depending on the results of the actual sea survey.
NTB 3 - Đồng Nai 2 (*) | 2x80 | 2031-2035 | New construction, synchronized with the scale and progress of offshore wind power sources in the South Central region. The length, cross-section and direction of the line will be precisely determined during the project implementation phase, depending on the results of the actual sea survey.
Đấu nối Trạm 765÷1000 kV Nam Trung Bộ 1 vào lưới 500 kV khu vực | 200 | 2031-2035 | New construction, in case of high development of South Central power source
Đấu nối Trạm 765÷1000 kV Nam Trung Bộ 2 vào lưới 500 kV khu vực | 200 | 2031-2035 | New construction, in case of high development of South Central power source
500 kV Lâm Đồng - Rẽ Ninh Sơn - Chơn Thành | 4x10 | 2031-2035 | New construction, connection of 500 kV Lam Dong substation
500 kV Tây Ninh 3 -500 kV Tây Ninh 2 (*) | 2x20 | 2031-2035 | New construction, release of renewable energy sources
Lộc Ninh - Chơn Thành (*) | 2x60 | 2031-2035 | New construction, release of renewable energy sources
Long Điền - Rẽ LNG Long Sơn - Bắc Châu Đức | 2x10 | 2031-2035 | New construction, connection of 500 kV Long Dien substation
LNG Long Sơn - Bắc Châu Đức | 2x36 | 2031-2035 | New construction, synchronized with Long Son LNG, depending on power source progress
500 kV Đồng Nai 4 - Rẽ Sông Mây - Tân Định (*) | 2x15 | 2031-2035 | New construction, renewable energy release
Đa Phước - Rẽ Phú Lâm - Nhà Bè | 2x8 | 2031-2035 | New construction and connection of 500 kV Da Phuoc station
Đa Phước - Long An | 2x10 | 2031-2035 | New construction, connection transfer to Ben Tre 500 kV substation
TP Thủ Đức - Long Thành | 2x25 | 2031-2035 | New construction and connection of 500 kV station in Thu Duc city
Đấu nối Trạm 765÷1000 kV Nam Bộ 1 vào lưới 500 kV khu vực | 4x200 | 2031-2035 | New construction, in case of high development of South Central power source
Đấu nối Trạm 765÷1000 kV Nam Bộ 2 vào lưới 500 kV khu vực | 4x200 | 2031-2035 | New construction, in case of high development of South Central power source
Tiền Giang - Rẽ Ô Môn - Mỹ Tho | 4x5 | 2031-2035 | New construction and connection of 500 kV Tien Giang substation
LNG Long An II - Long An | 2x15 | 2031-2035 | New construction, synchronous LNG Long An II
Long An 2 - Rẽ Sông Hậu - Đức Hòa | 2x13 | 2031-2035 | New construction, connection of 500 kV Long An 2 substation
500 kV Trà Vinh 2 - Duyên Hải | 4x1 | 2031-2035 | New construction, renewable energy release
500 kV Trà Vinh 2 - Bến Tre | 2x60 | 2031-2035 | New construction, renewable energy release
Đồng Tháp - Tây Ninh 1 | 2x112 | 2031-2035 | New construction
An Giang - Đồng Tháp | 2x65 | 2031-2035 | New construction
500 kV Bạc Liêu - An Giang (*) | 2x115 | 2031-2035 | New construction
Dự phòng phát sinh đường dây 500 kV cải tạo và xây mới | 500 | 2031-2035 | Provision for load growth and power source development

## Table 13 220kv transformers sou
Name | Capacity (MVA) | Time | Name
Bảo Lộc | 500 | 2025-2030 | Renovation and capacity improvement
Đức Trọng | 500 | 2025-2030 | Renovation and capacity improvement
Tà Năng (*) | 250 | 2025-2030 | New construction, renewable energy release
Bảo Lâm | 250 | 2025-2030 | Constructing a new, synchronous Alumina factory in Lam Dong (according to the request in Document No. 23/SCT-QLNL dated January 4, 2025 of Lam Dong Provincial Department of Industry and Trade)
Đạ Huoai | 250 | 2025-2030 | Constructing a new, synchronous Alumina factory in Lam Dong (according to the request in Document No. 23/SCT-QLNL dated January 4, 2025 of Lam Dong Provincial Department of Industry and Trade)
TĐ Đa Nhim | 375 | 2025-2030 | Renovation and capacity improvement
Phước Thái | 750 | 2025-2030 | Renovation and capacity improvement
Trạm cắt Đa Nhim | Trạm cắt | 2025-2030 | New construction
Cà Ná | 500 | 2025-2030 | New construction
Đông Quán Thẻ | 480 | 2025-2030 | New construction, synchronous specialized loads
TĐ Hàm Thuận | 125 | 2025-2030 | Renovation and capacity improvement
TĐ Đại Ninh | 250 | 2025-2030 | Renovation and capacity improvement
Hàm Thuận Nam | 500 | 2025-2030 | New construction
Vĩnh Hảo | 500 | 2025-2030 | Renovation and capacity improvement
Hòa Thắng (*) | 500 | 2025-2030 | New construction
Hồng Phong 500 kV nối cấp | 500 | 2025-2030 | New construction
Phong điện 1 Bình Thuận (*) | 250 | 2025-2030 | New construction, renewable energy release
Tân Sơn Nhất | 500 | 2025-2030 | New construction
Đầm Sen | 500 | 2025-2030 | New construction
Thủ Thiêm | 500 | 2025-2030 | New construction
Bình Chánh 1 | 500 | 2025-2030 | New construction
Bà Quẹo (Vĩnh Lộc) | 500 | 2025-2030 | New construction
Quận 7 | 500 | 2025-2030 | New construction
Nam Hiệp Phước | 500 | 2025-2030 | New construction
Quận 9 | 500 | 2025-2030 | New construction
Tây Bắc Củ Chi | 250 | 2025-2030 | New construction
Phú Hòa Đông | 250 | 2025-2030 | New construction
Cần Giờ | 500 | 2025-2030 | New construction
Phước Long | 500 | 2025-2030 | Renovation and capacity improvement
Đông Bình Phước (*) | 500 | 2025-2030 | New construction, renewable energy release
Alumin Bình Phước | 500 | 2025-2030 | Constructing a new, synchronous Binh Phuoc Alumina factory (according to the request in Document No. 1058/UBND-TH dated March 11, 2025 of Binh Phuoc Provincial People's Committee)
Đồng Xoài | 250 | 2025-2030 | New construction
Tân Biên | 500 | 2025-2030 | Renovation and capacity improvement
Phước Đông | 500 | 2025-2030 | New construction
Tây Ninh 3 | 250 | 2025-2030 | New construction
Tân Định | 750 | 2025-2030 | Renovation and capacity improvement
Bến Cát 2 | 500 | 2025-2030 | New construction
Tân Định 2 | 500 | 2025-2030 | New construction
An Thạnh (VSIP) | 500 | 2025-2030 | New construction
Bình Mỹ | 500 | 2025-2030 | New construction
Bắc Tân Uyên | 500 | 2025-2030 | New construction
Lai Uyên | 500 | 2025-2030 | New construction
Phú Giáo | 500 | 2025-2030 | New construction
TĐ Trị An | 500 | 2025-2030 | Renovation and capacity improvement
Tam Phước | 500 | 2025-2030 | Renovation and capacity improvement
Thống Nhất | 500 | 2025-2030 | New construction
KCN Nhơn Trạch | 500 | 2025-2030 | New construction
Long Khánh | 500 | 2025-2030 | Renovation and capacity improvement
Hố Nai | 500 | 2025-2030 | New construction
Dầu Giây | 500 | 2025-2030 | New construction
Biên Hòa | 500 | 2025-2030 | New construction
Đồng Nai 3 (*) | 750 | 2025-2030 | New construction, renewable energy release
Đồng Nai 4 (*) | 750 | 2025-2030 | New construction, renewable energy release
Bà Rịa | 250 | 2025-2030 | Renovation and capacity improvement
KCN Phú Mỹ 3 | 500 | 2025-2030 | New construction
Phước Thuận (Đất Đỏ) | 500 | 2025-2030 | New construction
Long Sơn | 250 | 2025-2030 | New construction
Cần Đước | 500 | 2025-2030 | Renovation and capacity improvement
Đức Hòa 2 | 500 | 2025-2030 | New construction
Đức Hòa 500 kV nối cấp | 500 | 2025-2030 | New construction
Bến Lức 2 (Đức Hòa 3) | 500 | 2025-2030 | Construct new and replace Duc Hoa 3 220 kV substation in Power Plan VIII (according to EVNNPT's proposal in Document No. 781/EVNNPT-KH+DT dated February 21, 2025).
Tân Lập | 250 | 2025-2030 | New construction
Kiến Tường | 250 | 2025-2030 | New construction
Lấp Vò | 250 | 2025-2030 | New construction
Hồng Ngự | 250 | 2025-2030 | New construction
Long Xuyên | 500 | 2025-2030 | Renovation and capacity improvement
Chợ Mới | 250 | 2025-2030 | New construction
Châu Thành (An Giang) | 250 | 2025-2030 | New construction
Cai Lậy | 500 | 2025-2030 | Renovation and capacity improvement
Mỹ Tho | 500 | 2025-2030 | Renovation and capacity improvement
Tân Phước (Cái Bè) | 500 | 2025-2030 | New construction
Gò Công | 500 | 2025-2030 | New construction
Vĩnh Long 3 | 250 | 2025-2030 | New construction
Mỏ Cày | 500 | 2025-2030 | Renovation and capacity improvement
Bình Đại (*) | 500 | 2025-2030 | New construction, renewable energy release
Thạnh Phú (*) | 500 | 2025-2030 | New construction, renewable energy release
An Biên (Vĩnh Thuận) | 500 | 2025-2030 | New construction
Phú Quốc | 500 | 2025-2030 | New construction
Trà Nóc | 500 | 2025-2030 | Renovation and capacity improvement
Ô Môn | 500 | 2025-2030 | Renovation and capacity improvement
Châu Thành (Hậu Giang) | 500 | 2025-2030 | Renovation and capacity improvement
Trà Vinh | 500 | 2025-2030 | Renovation and capacity improvement
Trà Vinh 3 | 450 | 2025-2030 | New construction, synchronized with the development progress of specialized loads
Trần Đề (*) | 500 | 2025-2030 | New construction, renewable energy release
Bạc Liêu | 375 | 2025-2030 | Renovation and capacity improvement
Giá Rai | 250 | 2025-2030 | Renovation and capacity improvement
Hòa Bình (*) | 500 | 2025-2030 | New construction
Bạc Liêu 3 (*) | 500 | 2025-2030 | New construction, renewable energy release
Cà Mau 3 | 450 | 2025-2030 | New construction, synchronized with the development progress of specialized loads
Năm Căn | 500 | 2025-2030 | New construction
Công suất dự phòng TBA cho tăng trưởng phụ tải và phát triển nguồn miền Nam | 3500 | 2025-2030 | Provision for new 220 kV substation construction and capacity upgrade
Lắp kháng hạn chế dòng ngắn mạch bao gồm nhưng không giới hạn tại các thanh cái TBA 500 kV Vĩnh Tân, Bắc Châu Đức, TBA Bà Quẹo (kháng đường dây 220kV Bà Quẹo - Đầm Sen) |  |  | Short circuit current limit
Cải tạo sơ đồ thanh cái linh hoạt, phân đoạn thanh cái bao gồm nhưng không giới hạn tại các TBA 500 kV Đức Hòa, Ô Môn, TBA Ninh Phước, Long Thành, Củ Chi |  |  | Limit short circuit current, increase power supply reliability
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | Including but not limited to projects: Replacing, installing electric resistors, capacitor banks, SVCs, SVGs, FACTS devices, BESSs, synchronous compensators...; expanding transformer station bays, renovating and completing transformer station diagrams in a flexible direction; installing short-circuit current limiting devices, replacing and upgrading devices to ensure short-circuit current tolerance, setting up automatic circuits; replacing devices to ensure synchronous load capacity of lines and transformers; installing, replacing devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...
Đà Lạt | 250 | 2031-2035 | New construction
220 kV Ninh Thuận 1 (*) | 750 | 2031-2035 | New construction, renewable energy release
220 kV Ninh Thuận 2 (*) | 750 | 2031-2035 | New construction, renewable energy release
220 kV Ninh Thuận 3 (*) | 750 | 2031-2035 | New construction, renewable energy release
Phong điện 1 Bình Thuận (*) | 500 | 2031-2035 | Renovation and capacity improvement
Hồng Liêm (*) | 250 | 2031-2035 | New construction, renewable energy release
Tây Bắc Củ Chi | 500 | 2031-2035 | Renovation and capacity improvement
Phú Hòa Đông | 500 | 2031-2035 | Renovation and capacity improvement
Bình Chánh 2 | 500 | 2031-2035 | New construction
Hóc Môn 2 | 500 | 2031-2035 | New construction
TP Thủ Đức 500 kV nối cấp | 750 | 2031-2035 | New construction
Đa Phước 500 kV nối cấp | 750 | 2031-2035 | New construction
Đông Bình Phước (*) | 750 | 2031-2035 | Renovation and capacity improvement
Đồng Xoài | 500 | 2031-2035 | Renovation and capacity improvement
Hớn Quản | 250 | 2031-2035 | New construction
220 kV Bình Phước 1 (*) | 750 | 2031-2035 | New construction, renewable energy release
220 kV Bình Phước 2 (*) | 750 | 2031-2035 | New construction, renewable energy release
Tây Ninh | 750 | 2031-2035 | Renovation and capacity improvement
Tây Ninh 2 | 750 | 2031-2035 | Renovation and capacity improvement
Bến Cầu | 500 | 2031-2035 | New construction
Tây Ninh 3 | 500 | 2031-2035 | Renovation and capacity improvement
Tân Châu 1 (*) | 500 | 2031-2035 | New construction, renewable energy release
Mỹ Phước | 750 | 2031-2035 | Renovation and capacity improvement
Uyên Hưng | 750 | 2031-2035 | Renovation and capacity improvement
Bến Cát | 750 | 2031-2035 | Renovation and capacity improvement
Tân Uyên | 750 | 2031-2035 | Renovation and capacity improvement
Bến Cát 2 | 750 | 2031-2035 | Renovation and capacity improvement
Tân Định 2 | 750 | 2031-2035 | Renovation and capacity improvement
An Thạnh (VSIP) | 750 | 2031-2035 | Renovation and capacity improvement
Bình Mỹ | 750 | 2031-2035 | Renovation and capacity improvement
Bến Cát 3 | 750 | 2031-2035 | New construction
Bàu Bàng | 750 | 2031-2035 | New construction
Bình Dương 2 500 kV nối cấp | 750 | 2031-2035 | New construction
Long Thành | 750 | 2031-2035 | Renovation and capacity improvement
An Phước | 750 | 2031-2035 | Renovation and capacity improvement
Tam Phước | 750 | 2031-2035 | Renovation and capacity improvement
KCN Nhơn Trạch | 750 | 2031-2035 | Renovation and capacity improvement
Biên Hòa | 750 | 2031-2035 | Renovation and capacity improvement
Đồng Nai 3 (*) | 1000 | 2031-2035 | Renovation and capacity improvement
Đồng Nai 4 (*) | 1000 | 2031-2035 | Renovation and capacity improvement
Long Thành 500 kV nối cấp | 750 | 2031-2035 | New construction
KCN Long Thành 2 | 750 | 2031-2035 | New construction
Đồng Nai 2 500 kV nối cấp | 750 | 2031-2035 | New construction
Long Sơn | 500 | 2031-2035 | Renovation and capacity improvement
TP Phú Mỹ | 500 | 2031-2035 | New construction
Vũng Tàu 2 | 500 | 2031-2035 | New construction
Đức Hòa 500 kV nối cấp | 750 | 2031-2035 | Renovation and capacity improvement
Tân Lập | 500 | 2031-2035 | Renovation and capacity improvement
Cần Giuộc | 500 | 2031-2035 | New construction
Kiến Tường | 500 | 2031-2035 | Renovation and capacity improvement
Long An 2 500 kV nối cấp | 500 | 2031-2035 | New construction
Lấp Vò | 500 | 2031-2035 | Renovation and capacity improvement
Hồng Ngự | 500 | 2031-2035 | Renovation and capacity improvement
Đồng Tháp 500 kV nối cấp | 250 | 2031-2035 | New construction
Chợ Mới | 500 | 2031-2035 | Renovation and capacity improvement
Châu Thành (An Giang) | 500 | 2031-2035 | Renovation and capacity improvement
An Giang 500 kV nối cấp | 250 | 2031-2035 | New construction
Tân Phước (Cái Bè) | 750 | 2031-2035 | Renovation and capacity improvement
Tiền Giang 500 kV nối cấp | 500 | 2031-2035 | New construction
Vĩnh Long 3 | 500 | 2031-2035 | Renovation and capacity improvement
Ba Tri | 500 | 2031-2035 | New construction
Vĩnh Quang | 250 | 2031-2035 | New construction
Thốt Nốt | 500 | 2031-2035 | Renovation and capacity improvement
Vị Thanh | 250 | 2031-2035 | New construction
Duyên Hải | 500 | 2031-2035 | Renovation and capacity improvement
Bạc Liêu | 500 | 2031-2035 | Renovation and capacity improvement
Giá Rai | 500 | 2031-2035 | Renovation and capacity improvement
Bạc Liêu 4 (*) | 500 | 2031-2035 | New construction, renewable energy release
Cà Mau 4 | 250 | 2031-2035 | New construction, renewable energy release
Công suất dự phòng TBA cho tăng trưởng phụ tải và phát triển nguồn miền Nam | 3500 | 2031-2035 | Provision for new 220 kV substation construction and capacity upgrade
Các công trình, dự án nâng cao khả năng điều khiển và vận hành trạm điện, hệ thống điện |  |  | Including but not limited to projects: Replacing, installing electric resistors, capacitor banks, SVCs, SVGs, FACTS devices, BESSs, synchronous compensators...; expanding transformer station bays, renovating and completing transformer station diagrams in a flexible direction; installing short-circuit current limiting devices, replacing and upgrading devices to ensure short-circuit current tolerance, setting up automatic circuits; replacing devices to ensure synchronous load capacity of lines and transformers; installing, replacing devices, control systems, SCADA/EMS systems, SCADA/DMS, station automation,...

## Table 14 220 kV lines in the So
Name | Number of circuits × kilometres | Time | Note
Mạch 2 Bảo Lộc - Sông Mây | 2x118 | 2025-2030 | Renovate circuit 1, build circuit 2, improve reliability
Trạm cắt 220 kV Đa Nhim - Rẽ Tháp Chàm - Đa Nhim | 2x1 | 2025-2030 | New construction, synchronized 220 kV Da Nhim switching station
Trạm cắt 220 kV Đa Nhim - Đức Trọng - Di Linh | 2x96 | 2025-2030 | New construction, clearing the power source in the area. Replacing the project to renovate the 220 kV Da Nhim - Duc Trong - Di Linh line from 01 circuit to 02 circuits due to difficulties in cutting off power to construct the existing line and not being able to expand the 220 kV Da Nhim substation.
TĐ Đồng Nai 2 - Rẽ Đức Trọng - Di Linh và chuyển đấu nối (Đức Trọng - TĐ Đồng Nai 2 thay cho Đức Trọng - Di Linh), cải tạo nâng khả năng tải ĐD 220 kVTĐ Đồng Nai 2-Di Linh | 1x15 | 2025-2030 | New construction and renovation, forming the 220 kV single circuit Duc Trong - Dong Nai 2 - Di Linh substation to replace the 220 kV double circuit Dong Nai 2 - Di Linh substation
Đức Trọng - Rẽ trạm cắt 220 kV Đa Nhim - Di Linh | 2x1 | 2025-2030 | New construction, regional power source release
Bảo Lâm - Bảo Lộc | 2x25 | 2025-2030 | New construction, synchronized with the progress of the Alumina factory in Lam Dong
Đạ Huoai - Rẽ Bảo Lộc - Định Quán | 2x2 | 2025-2030 | New construction, synchronized with the progress of the Alumina factory in Lam Dong
ĐG Đức Trọng - Rẽ Đa Nhím - Đức Trọng (*) | 2x1 | 2025-2030 | Newly build and synchronize Duc Trong wind power plant. The location and adjusted connection plan of Duc Trong wind power plant are proposed in Document No. 3225/BCT-DL dated June 9, 2022, Document No. 4777/BCT-DL dated August 11, 2022, Document No. 6660/BCT-DL dated October 26, 2022 of the Ministry of Industry and Trade and Document No. 835/TTg-CN dated September 22, 2022 of the Prime Minister. Synchronously operate with the 220 kV transmission line of Da Nhim - Duc Trong - Di Linh switching station.
Tà Năng - rẽ Đức Trọng - Di Linh (*) | 2x20 | 2025-2030 | New construction and connection of 220 kV Ta Nang substation on 220 kV Duc Trong - Di Linh line (new construction circuit). Synchronized with the scale and progress of regional power sources
Đấu nối TĐ Đa R'Sal (**) | 1x30 | 2025-2030 | New construction, synchronization of power source. Document No. 23/SCT-QLNL dated January 4, 2025 of Lam Dong Provincial Department of Industry and Trade proposed connecting Da R'Sal Power Plant to 220 kV TC, 220 kV TD Buôn Tua Srah Substation. The specific connection plan is accurate during the project implementation phase.
500 kV Ninh Sơn - Rẽ Tháp Chàm - Ninh Phước | 4x27 | 2025-2030 | New construction and connection of 500 kV Ninh Son substation
500 kV Ninh Sơn - Ninh Phước | 2x47 | 2025-2030 | New construction, replacement for Ninh Phuoc - Vinh Tan 220 kV line due to difficulties in route direction
500 kV Ninh Sơn - Trạm cắt 220 kV Đa Nhim | 2x18 | 2025-2030 | New construction, regional power source release
Tháp Chàm - trạm cắt 220 kV Đa Nhim | 2x46 | 2025-2030 | New construction, regional power source release
500 kV Vĩnh Tân - Cà Ná | 2x14 | 2025-2030 | New construction, connection to 220 kV Ca Na station
ĐG Phước Hữu - 220 kV Ninh Phước (*) | 1x2 | 2025-2030 | New construction, connection to Phuoc Huu DG, replacing the 110 kV Phuoc Huu DG - 110 Ky Ninh Phuoc DG approved in Decision No. 3768/QD-BCT dated July 27, 2011 because the 110 kV grid is not capable of clearing. The 220 kV Phuoc Huu DG step-up station has a capacity of 63 MVA.
Đông Quán Thẻ - Rẽ Vĩnh Tân - Trạm cắt 220 kV Quán Thẻ | 2x1 | 2025-2030 | New construction, synchronized with the development progress of specialized loads
Đông Quán Thẻ - Cà Ná | 1x7 | 2025-2030 | New construction, synchronized with the development progress of specialized loads
TĐ Đa Nhim MR GĐ2 - Sân phân phối 220 kV Đa Nhim | 1x1 | 2025-2030 | New construction, synchronized power source. Proposed plan in Document No. 862/EVN-KH of EVN dated February 11, 2025. Specific connection plan is accurate during project implementation phase.
Hàm Tân - Rẽ Phan Thiết - Châu Đức (mạch 2) | 2x6 | 2025-2030 | New construction, connection of Ham Tan 220 kV station to relay on the remaining circuit of Phan Thiet - Tan Thanh 220 kV line
Hàm Thuận Nam - Rẽ Phan Thiết - Hàm Tân | 4x4 | 2025-2030 | New construction and connection of 220 kV Ham Thuan Nam substation
Hòa Thắng - Rẽ Phan Thiết - Phan Rí | 2x7 | 2025-2030 | New construction and connection of 220 kV Hoa Thang substation
Nâng khả năng tải Hàm Thuận - Đa My - Xuân Lộc | 2x95 | 2025-2030 | Upgrade to increase load capacity
Nâng khả năng tải Phan Thiết - Hàm Thuận | 1x55 | 2025-2030 | Upgrade to increase load capacity
Phước Thái - Rẽ Vĩnh Tân - Tháp Chàm (mạch 2) | 2x3 | 2025-2030 | New construction, connection of Phuoc Thai 220 kV station to relay on the remaining circuit of Vinh Tan - Thap Cham 220 kV line, relieving power source in the area
Hồng Phong - Rẽ Phan Thiết - Phan Rí | 2x1 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
Phong điện 1 Bình Thuận - Rẽ Vĩnh Tân - Phan Thiết (*) | 2x4 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
Nâng khả năng tải Phan Rí - Phan Thiết | 2x52 | 2025-2030 | Renovating to increase load capacity and unifying cross-section on the entire 220 kV Phan Ri - Phan Thiet line to relieve regional power sources
Phan Rí - 500 kV Hồng Phong | 2x16 | 2025-2030 | New construction, increased capacity to release regional power
500 kV Hồng Phong - Rẽ Phan Rí - Phan Thiết | 4x5 | 2025-2030 | New construction and connection of 500 kV Hong Phong station
500 kV Sơn Mỹ - Rẽ Hàm Tân - Phước Thuận (Đất Đỏ) | 4x4 | 2025-2030 | New construction
Nâng khả năng tải Bình Long - Chơn Thành | 2x32 | 2025-2030 | Improve load capacity and relieve regional power sources
Tân Biên - Tây Ninh | 2x25 | 2025-2030 | New construction
500 kV Tây Ninh 1 - Rẽ Tây Ninh 2 - Trảng Bàng | 4x8 | 2025-2030 | New construction
500 kV Tây Ninh 1 - Phước Đông | 2x8 | 2025-2030 | New construction
Alumin Bình Phước - Rẽ Phước Long - Điện phân nhôm | 2x15 | 2025-2030 | Constructing a new, synchronous Binh Phuoc Alumina factory (according to the request in Document No. 1058/UBND-TH dated March 11, 2025 of Binh Phuoc Provincial People's Committee)
Đồng Xoài - Chơn Thành | 2x20 | 2025-2030 | New construction
Bình Long - Chơn Thành (mạch 3, 4) | 2x32 | 2025-2030 | New construction, regional power source release
Đông Bình Phước - Rẽ Bình Long - Điện phân nhôm (*) | 4x12 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
Nâng khả năng tải ĐD 220 kV Chơn Thành 500 kV -Mỹ Phước | 2x45 | 2025-2030 | Improve load capacity and relieve regional power sources
Nâng khả năng tải ĐD 220 kV Mỹ Phước - Tân Định 500 kV | 2x17 | 2025-2030 | Improve load capacity and relieve regional power sources
500 kV Tây Ninh 2 - Rẽ ĐMT Hồ Dầu Tiếng - Tây Ninh | 4x3 | 2025-2030 | New construction, connection to 220 kV side of 500 kV Tay Ninh 2 station
500 kV Tây Ninh 2 - Tây Ninh (chuyển đấu nối đi Tân Biên) | 2x6 | 2025-2030 | New construction, connection to 220 kV side of 500 kV Tay Ninh 2 station
Tây Ninh 3 - 500 kV Tây Ninh 2 | 2x16 | 2025-2030 | New construction
Nâng khả năng tải Phú Mỹ - Long Thành | 2x25 | 2025-2030 | Upgrade to increase load capacity
Nâng khả năng tải Phú Mỹ - Tân Thành | 2x11 | 2025-2030 | Upgrade to increase load capacity
KCN Phú Mỹ 3 - Rẽ Tân Thành - Châu Đức | 4x1 | 2025-2030 | New construction
500 kV Bắc Châu Đức - Rẽ Châu Đức - Tân Thành | 4x10 | 2025-2030 | New construction
Phước Thuận (Đất Đỏ) - Rẽ Phan Thiết - Tân Thành và Hàm Tân - Tân Thành | 4x6 | 2025-2030 | New construction
Long Sơn - Rẽ Châu Đức - KCN Phú Mỹ 3 | 2x8 | 2025-2030 | New construction, consider choosing a cross-section suitable for the cross-section of Chau Duc 220 kV line - Phu My 3 Industrial Park after renovation
Châu Đức - rẽ Hàm Tân - Tân Thành (mạch 2) | 2x2 | 2025-2030 | New construction, completion of connection of Chau Duc 220kV substation to 02 circuits of Ham Tan - Tan Thanh 220kV transmission line
Nâng khả năng tải Tân Thành - Vũng Tàu | 2x30 | 2025-2030 | Upgrade to increase load capacity
Nâng khả năng tải Hàm Tân - Châu Đức và Hàm Tân - ĐMT Đá Bạc - Châu Đức | 2x60 | 2025-2030 | Improve load capacity and relieve regional power sources
Cát Lái - Tân Cảng | 2x15 | 2025-2030 | New construction
Bình Chánh 1 - Cầu Bông | 2x21 | 2025-2030 | New construction, part of the 220-110 kV Cau Bong - Binh Tan transmission line project
Tân Sơn Nhất - Thuận An | 2x15 | 2025-2030 | New construction
Tân Sơn Nhất - Rẽ Hóc Môn - Thủ Đức | 2x9 | 2025-2030 | New construction
Phú Lâm - Đầm Sen | 2x6 | 2025-2030 | New construction
Đầm Sen - Bà Quẹo - Tân Sơn Nhất | 2x10 | 2025-2030 | New construction
500 kV Long Thành - Công Nghệ Cao | 2x25 | 2025-2030 | New construction
500 kV Củ Chi - Rẽ Củ Chi - Trảng Bàng | 4x1 | 2025-2030 | New construction, connection conversion to 220 kV Cu Chi 500 kV - Trang Bang and Cu Chi 500 kV - Tan Dinh transmission lines
500 kV Củ Chi - Rẽ Củ Chi - Tân Định | 2x1 | 2025-2030 | New construction, connection conversion to 220 kV Cu Chi 500 kV - 220 kV Cu Chi
Thủ Thiêm - Rẽ Cát Lái - Tân Cảng | 4x1 | 2025-2030 | New construction
Quận 7 - Nhà Bè và mở rộng ngăn lộ 220 kV tại trạm 500 kV Nhà Bè | 2x6 | 2025-2030 | New construction, connection to 220 kV station in District 7, in case the 220 kV compartment at 500 kV station in Nha Be cannot be expanded, consider connecting District 7 - Nhon Trach 1 & 2 ND branch - Nha Be (2x7km), using large cross-section
Quận 9 - Rẽ Long Thành - Công nghệ cao | 4x5 | 2025-2030 | New construction
LNG Hiệp Phước giai đoạn I - Rẽ Phú Mỹ - Cần Đước | 4x3 | 2025-2030 | New construction, synchronous LNG Hiep Phuoc phase I
Nâng khả năng tải ĐD 220 kV Phú Mỹ - Cần Đước - Mỹ Tho - Mỹ Tho 500 kV | 2x112 | 2025-2030 | Upgrade to increase loading capacity, synchronize LNG Hiep Phuoc phase I
Nâng khả năng tải Phú Mỹ - Tân Thành | 2x11 | 2025-2030 | Upgrade to increase load capacity
Nam Hiệp Phước - Rẽ Phú Mỹ - Cần Đước | 4x2 | 2025-2030 | New construction, connection to Nam Hiep Phuoc 220 kV station. Proposal to select suitable cross-section for Phu My - Can Duoc 220 kV line after renovation
Cần Giờ - Rẽ Phú Mỹ - Nam Hiệp Phước | 2x28 | 2025-2030 | New construction
Bến Cát 2 - Rẽ Tân Định - Củ Chi | 4x1 | 2025-2030 | New construction
Bến Cát 2 - Rẽ Chơn Thành - Bến Cát | 2x20 | 2025-2030 | New construction and transition connection to 01 circuit of 220 kV Chon Thanh - Ben Cat transmission line
Tân Định 2 - Rẽ Mỹ Phước - Bến Cát | 4x11 | 2025-2030 | New construction
500 kV Bình Dương 1 - Rẽ Uyên Hưng - Sông Mây | 4x40 | 2025-2030 | New construction and connection of 500 kV Binh Duong 1 substation
An Thạnh (VSIP) - Rẽ Tân Uyên - Thuận An | 4x3 | 2025-2030 | New construction
Bình Mỹ - Rẽ Bình Dương 1 - Sông Mây | 4x3 | 2025-2030 | New construction
Lai Uyên - Rẽ Chơn Thành - Bến Cát | 4x1 | 2025-2030 | New construction
Bắc Tân Uyên - Rẽ Bình Mỹ - Sông Mây | 2x7 | 2025-2030 | New construction
Sông Mây - Tam Phước | 2x14 | 2025-2030 | New construction
500 kV Đồng Nai 2 - Rẽ Xuân Lộc - Long Thành | 4x12 | 2025-2030 | New construction
NMĐ Nhơn Trạch 3 - Rẽ Mỹ Xuân - Cát Lái | 2x10 | 2025-2030 | Newly build and synchronize Nhon Trach 3 Power Plant; replace Nhon Trach 3 Power Plant - Cat Lai Line (connection to Thu Duc) due to difficulties in the construction direction of the line
NMĐ Nhơn Trạch 3 - 500 kV Long Thành | 2x44 | 2025-2030 | New and synchronous construction of Nhon Trach 3 Power Plant
KCN Nhơn Trạch - Rẽ NMĐ Nhơn Trạch 3 - 500 kV Long Thành | 4x3 | 2025-2030 | Newly build and synchronize the 220 kV station of Nhon Trach Industrial Park. In case Nhon Trach 3 Power Plant is behind schedule, consider building the 220 kV transmission line of Nhon Trach - Long Thanh Industrial Park first.
Nâng khả năng tải Sông Mây - Long Bình (mạch 1) | 1x16 | 2025-2030 | Upgrade to increase load capacity
Nâng khả năng tải Sông Mây - Long Bình (mạch 2) | 1x25 | 2025-2030 | Upgrade to increase load capacity
Thống Nhất - Rẽ Bảo Lộc - Sông Mây | 4x2 | 2025-2030 | New construction
Nâng khả năng tải Tân Định - Bình Hòa | 2x11 | 2025-2030 | Upgrade to increase load capacity
TĐ Trị An mở rộng - TĐ Trị An | 2x1 | 2025-2030 | New and synchronous construction of Tri An expansion plant
Tây Bắc Củ Chi - Củ Chi 500 kV | 2x12 | 2025-2030 | New construction
Bình Chánh 1 - Đức Hòa | 2x10 | 2025-2030 | New construction
Phú Hòa Đông - Rẽ Củ Chi - Cầu Bông | 4x5 | 2025-2030 | New construction
Nâng khả năng tải cầu Bông - Củ Chi | 2x22 | 2025-2030 | Upgrade to increase load capacity
Nâng khả năng tải cầu Bông - Bình Tân - Phú Lâm | 2x34 | 2025-2030 | Upgrade to increase load capacity
Nâng khả năng tải Thủ Đức - Tân Uyên - Long Bình | 2x44 | 2025-2030 | Upgrade to increase load capacity, consider the appropriate load capacity of the existing underground cable section
Tân Định 2 - Bình Mỹ | 2x14 | 2025-2030 | New construction
Biên Hòa - Rẽ Tân Uyên - Long Bình | 4x1 | 2025-2030 | New construction
Dầu Giây - 500 kV Đồng Nai 2 | 2x30 | 2025-2030 | New construction
Dầu Giây - 500 kV Long Thành | 2x12 | 2025-2030 | New construction
220 kV Đồng Nai 3 - Tân Uyên (*) | 2x55 | 2025-2030 | Synchronize with regional power source scale and progress
220 kV Đồng Nai 4 - Uyên Hưng (*) | 2x31 | 2025-2030 | Synchronize with regional power source scale and progress
Nâng khả năng tải 220 kV Long Thành - An Phước - Tam Phước | 2x16 | 2025-2030 | Upgrade to increase load capacity. Recommended to use large cross-section phase wires
Nâng khả năng tải 500 kV Long Thành - 220 kV Long Thành | 2x19 | 2025-2030 | Upgrade to increase load capacity
Hố Nai - Rẽ Sông Mây - Tam Phước | 4x1 | 2025-2030 | New construction
Phú Giáo - Rẽ Bình Dương 1 - Uyên Hưng | 4x2 | 2025-2030 | New construction
Nâng khả năng tải Long An - Bến Lức | 2x14 | 2025-2030 | Upgrade to increase load capacity
Gò Công - Cần Đước | 2x27 | 2025-2030 | New construction
500 kV Đức Hòa - Rẽ Phú Lâm - Long An (mạch 2) | 2x20 | 2025-2030 | New construction, connection of 220 kV side to 500 kV Duc Hoa station, transitioning on the remaining circuit of 220 kV Phu Lam - 500 kV Long An transmission line
Đức Hòa 2 - Rẽ 500 kV Đức Hòa - Đức Hòa 1 | 4x10 | 2025-2030 | New construction
Bến Lức 2 (Đức Hòa 3) đấu nối chuyển tiếp trên các ĐD 220 kV Đức Hoà 500 kV - Phú Lâm và ĐD 220 kV Đức Hoà 500 kV - Bến Lức. | 4x6 | 2025-2030 | New construction, replacement of Duc Hoa 3 220 kV line, forward connection on Duc Hoa 500 kV 220 kV line - Phu Lam branch - Long An in Power Planning VIII
Treo dây mạch 3,4 ĐD 220 kV Đức Hòa 500 kV - Đức Hòa 1 | 2x25 | 2025-2030 | Consider transferring connection to 220 kV Northwest Cu Chi station
500 kV Long An - Rẽ Cần Đước - Phú Mỹ | 4x1 | 2025-2030 | New construction
Nâng khả năng tải Bến Lức - Phú Lâm | 2x28 | 2025-2030 | Upgrade to increase load capacity
Tân Lập - Rẽ 500 kV Đức Hòa - Long An | 4x9 | 2025-2030 | New construction
Kiến Tường - Tân Lập | 2x40 | 2025-2030 | New construction. In case Tan Lap 220 kV substation is slow to come into operation, invest first in Kien Tuong 220 kV - Duc Hoa 500 kV - Long An line (2x50 km)
LNG Long An I - 500 kV Long An | 2x18 | 2025-2030 | New construction, synchronized with LNG Long An I, depending on power source progress; proposed design of 220 kV LNG Long An I distribution yard with flexible busbar segment diagram.
LNG Long An I - Bến Lức | 2x30 | 2025-2030 | New construction, synchronized with LNG Long An I, depending on power source progress; proposed design of 220 kV LNG Long An I SPP with flexible busbar segment diagram
Tân Phước (Cái Bè) - Rẽ 500 kV Mỹ Tho - Long An | 4x7 | 2025-2030 | New construction
Mỹ Tho - Rẽ Mỹ Tho 500 kV - Cần Đước (mạch 2) | 2x4 | 2025-2030 | New construction, connection of 220 kV My Tho station to relay on the remaining circuit of 220 kV My Tho - 500 kV Can Duoc line
Cần Đước - Rẽ Phú Mỹ 500 kV - Mỹ Tho (mạch 2) | 2x5 | 2025-2030 | New construction, connection of 220 kV station needs to be transferred on the remaining circuit of 220 kV Phu My - 500 kV My Tho line
ĐG Long Mỹ 1 - Rẽ NĐ Cà Mau - Ô Môn (*) | 2x1 | 2025-2030 | New construction, synchronous Long My 1 Highway
Vĩnh Long 3 - Rẽ Vĩnh Long 2 - Trà Vinh | 4x1 | 2025-2030 | New construction
Bến Tre - Bình Đại (*) | 2x50 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
Thạnh Phú - Rẽ ĐG Hải Phong - Mỏ Cày (*) | 4x3 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources. In case Hai Phong power plant is slow to enter, it is necessary to build the 220 kV Thanh Phu - Mo Cay double-circuit transmission line in advance, synchronized with the 220 kV Thanh Phu station, Hai Phong power plant connects to the 220 kV Thanh Phu station via the 220 kV double-circuit. Consider choosing a large cross-section to release renewable energy.
Mỏ Cày - 500 kV Mỹ Tho (*) | 2x42 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
An Biên (Vĩnh Thuận) - Rẽ NĐ Cà Mau - Rạch Giá | 2x17 | 2025-2030 | New construction
Trà Vinh 3 - 500 kV Duyên Hải | 2x3 | 2025-2030 | New construction, synchronized with Tra Vinh 3 220 kV station
ĐG số 19 Bến Tre - Bình Đại (*) | 2x12 | 2025-2030 | Newly build and synchronize Ben Tre No. 19 Power Line, relieve the capacity of Ben Tre No. 19 Power Line, Ben Tre No. 20 Power Line. Adjust the plan compared to Document 911/TTg-CN , replace the 220 kV Power Line No. 19 Ben Tre - Ben Tre, about 50km long due to difficulty in expanding the bypass at Ben Tre 220 kV station. Actual length is about 0.03km.
ĐG Hải Phong - Mỏ Cày (*) | 2x50 | 2025-2030 | New construction, synchronous Hai Phong Highway, connection plan approved in Document 911/TTg-CN dated July 15, 2020
ĐG Đông Thành 1 - 500 kV Duyên Hải (*) | 2x4 | 2025-2030 | Newly build and synchronize Dong Thanh 1 Power Line, relieve the capacity of Dong Thanh 1 Power Line, Dong Thanh 2 Power Line. Adjust the plan compared to Document 911/TTg-CN , replace the 220 kV Dong Thanh 1 Power Line - Dong Hai 1 Branch - Duyen Hai 500 kV to avoid overloading the 220 kV Dong Hai 1 Power Line - Trung Nam Tra Vinh Power Line - Duyen Hai 500 kV
ĐG Thăng Long - 220 kV Duyên Hải (*) | 1x12 | 2025-2030 | New construction, synchronous Thang Long Highway, connection plan approved in Document 911/TTg-CN dated June 24, 2020
500 kV Bến Tre - Rẽ Bình Đại - Bến Tre | 4x16 | 2025-2030 | New construction and connection of 500 kV Ben Tre substation
500 kV Bến Tre - Rẽ Thạnh Phú - Mỏ Cày | 4x10 | 2025-2030 | New construction and connection of 500 kV Ben Tre substation
500 kV Thốt Nốt - Lấp Vò | 2x22 | 2025-2030 | New construction
Hồng Ngự - Châu Đốc | 2x40 | 2025-2030 | New construction
Lấp Vò - Hồng Ngự | 2x55 | 2025-2030 | New construction
Sa Đéc - Rẽ Ô Môn - Vĩnh Long (mạch 2) | 2x1 | 2025-2030 | New construction, connection of 220 kV Sa Dec station to relay on the remaining circuit of 220 kV O Mon - Vinh Long line
Long Xuyên - Rẽ Châu Đốc - Thốt Nốt (mạch 2) | 2x1 | 2025-2030 | New construction, connecting 220 kV Long Xuyen station to relay on the remaining circuit of 220 kV Chau Doc - Thot Not line
Châu Thành (An Giang) - Rẽ Long Xuyên - Châu Đốc | 4x2 | 2025-2030 | New construction
Chợ Mới - Châu Thành (An Giang) | 2x9 | 2025-2030 | New construction
Cải tạo ĐD 220 kV Châu Đốc - Kiên Bình 1 mạch thành 2 mạch | 2x75 | 2025-2030 | Converting 1-circuit line into 2-circuit line, increasing load capacity
Trần Đề - 500 kV Long Phú | 2x24 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
Vĩnh Châu - Rẽ Long Phú - Sóc Trăng (mạch 2) | 2x20 | 2025-2030 | New construction, connection of 220 kV Vinh Chau station to the remaining circuit of 220 kV Long Phu - Soc Trang line
ĐG Sóc Trăng 4 - Vĩnh Châu (*) | 2x5 | 2025-2030 | New construction, synchronization of Soc Trang 4 Highway, connection plan approved in Document 911/TTg-CN dated June 24, 2020
ĐG Phú Cường 1A, 1B - Vĩnh Châu (*) | 2x22 | 2025-2030 | Newly and synchronously construct Phu Cuong 1A and 1B power lines; connection plan approved in Document 911/TTg-CN dated June 24, 2020
ĐG Bạc Liêu GĐ3 - Bạc Liêu (*) | 2x18 | 2025-2030 | New construction, synchronous Bac Lieu Phase 3, connection plan approved in Decision No. 209/QD-TTg dated February 9, 2018
Đường dây 220 kV mạch kép đấu nối TBA 220 kV Bạc Liêu chuyển tiếp trên ĐD 220 kV NĐ Cà Mau - Sóc Trăng | 2x5 | 2025-2030 | New construction, clearing of regional power sources; exact name of the project approved in Document No. 441/TTg-CN dated April 16, 2020 "Double-circuit 220 kV transmission line connecting Bac Lieu 220 kV substation, transitioning on Ca Mau - Bac Lieu thermal power line"
Hòa Bình - Rẽ Giá Rai - Bạc Liêu | 2x13 | 2025-2030 | New construction, connection of 220 kV Hoa Binh station (Bac Lieu province) to transfer 220 kV Gia Rai - Bac Lieu line, relieving power source in the area
Hòa Bình đấu nối chuyển tiếp trên ĐD 220 kV đấu nối ĐG Hòa Bình 5 | 4x5 | 2025-2030 | New construction and connection of 220 kV Hoa Binh station (Bac Lieu province), relieving power shortage in the area
Bạc Liêu 3 - 500 kV Bạc Liêu (*) | 2x30 | 2025-2030 | New construction, synchronized with the scale and progress of regional power sources
500 kV Bạc Liêu - Rẽ Giá Rai - Hòa Bình | 4x6 | 2025-2030 | New construction, synchronization of 500 kV Bac Lieu station
500 kV Bạc Liêu - Hòa Bình | 2x18 | 2025-2030 | New construction, renewable energy release
Cà Mau - Năm Căn | 2x58 | 2025-2030 | New construction
Cà Mau 3 - Rẽ Cà Mau - Năm Căn | 2x26 | 2025-2030 | New construction, synchronization of 220 kV Ca Mau 3 station
Cụm ĐG Cà Mau 1 - Cà Mau (*) | 2x52 | 2025-2030 | New and synchronous construction of Ca Mau 1 Highway Cluster
500 kV Cà Mau - Rẽ Năm Căn - Cà Mau | 4x8 | 2025-2030 | New construction
500 kV Cà Mau - Rẽ ĐG Cà Mau 1 - Cà Mau | 4x8 | 2025-2030 | New construction
NB 1 - Vũng Tàu (*) | 2x3 | 2025-2030 | New construction, synchronized with the scale and progress of offshore wind power sources in the South. The length, cross-section and direction of the line will be precisely determined during the project implementation phase, depending on the results of the actual sea survey.
NB 2 - Bến Tre 500kV (*) | 2x10 | 2025-2030 | New construction, synchronized with the scale and progress of offshore wind power sources in the South. The length, cross-section and direction of the line will be precisely determined during the project implementation phase, depending on the results of the actual sea survey.
NB 3 - 500 kV Duyên Hải (*) | 2x10 | 2025-2030 | New construction, synchronized with the scale and progress of offshore wind power sources in the South. The length, cross-section and direction of the line will be precisely determined during the project implementation phase, depending on the results of the actual sea survey.
Đấu nối TBA 220kV Phú Quốc | 2x19 | 2025-2030 | Constructing a new 220kV line from Phu Quoc 220kV substation connecting to the existing Kien Binh - Phu Quoc 220kV line, synchronized with Phu Quoc 220kV substation
Ước tính khối lượng đấu nối các nguồn NLTT | 500 | 2025-2030 | New construction, renewable energy release
Dự phòng phát sinh ĐZ 220 kV cải tạo và xây mới | 450 | 2025-2030 | Provision for load growth and power source development
Hồng Liêm - 500 kV Hồng Phong (*) | 2x6 | 2031-2035 | New construction, release of renewable energy sources
Đà Lạt - Trạm cắt 220 kV Đa Nhim | 2x30 | 2031-2035 | New construction
Nâng khả năng tải Di Linh - Bảo Lộc | 2x34 | 2031-2035 | Upgrade to increase load capacity
220 kV Ninh Thuận 1- 500 kV Ninh Thuận 1 (*) | 2x15 | 2031-2035 | New construction, release of renewable energy sources
220 kV Ninh Thuận 2 - 500 kV Ninh Thuận 1 (*) | 2x15 | 2031-2035 | New construction, release of renewable energy sources
220 kV Ninh Thuận 3 - 500 kV Ninh Thuận 2 (*) | 2x15 | 2031-2035 | New construction, release of renewable energy sources
Tân Châu 1 - Tân Biên (*) | 2x16 | 2031-2035 | New construction, synchronized with the scale and progress of regional power sources
Bến Cầu - 500 kV Tây Ninh 1 | 2x12 | 2031-2035 | New construction
Hớn Quản - Rẽ Bình Long - Chơn Thành | 2x4 | 2031-2035 | New construction
220 kV Bình Phước 1 - 500 kV Lộc Ninh (*) | 2x15 | 2031-2035 | New construction, release of renewable energy sources
220 kV Bình Phước 2 - 500 kV Lộc Ninh (*) | 2x15 | 2031-2035 | New construction, release of renewable energy sources
TP Phú Mỹ - Rẽ Phú Mỹ - Bà Rịa | 4x2 | 2031-2035 | Upgrade to increase load capacity
TP Phú Mỹ - Bắc Châu Đức 500 kV | 2x30 | 2031-2035 | New construction
Long Điền 500 kV - Vũng Tàu 2 | 2x13 | 2031-2035 | New construction, connection of 500 kV Long Dien substation
Long Điền 500 kV - Rẽ TP Phú Mỹ - Vũng Tàu | 2x10 | 2031-2035 | New construction, connection of 500 kV Long Dien substation
Long Điền 500 kV - Phước Thuận (Đất Đỏ) | 2x16 | 2031-2035 | New construction, connection of 500 kV Long Dien substation
Vũng Tàu 2 - Vũng Tàu | 2x9 | 2031-2035 | New construction
Nâng khả năng tải TĐ Trị An - Sông Mây 500 kV | 1x24 | 2031-2035 | Upgrade load capacity to ensure regional power supply
Bình Chánh 2 - Rẽ Đức Hòa - Phú Lâm | 4x2 | 2031-2035 | New construction, flexible design proposal for 220 kV Binh Chanh 2 substation
500 kV Đa Phước - Bình Chánh 2 | 2x10 | 2031-2035 | New construction, connection of 500 kV Da Phuoc substation. 220 kV Binh Chanh 2 substation with flexible design diagram
500 kV Đa Phước - Bình Chánh | 2x9 | 2031-2035 | New construction, connection of 500 kV Da Phuoc substation, consideration of transferring connection of 220 kV District 8 substation to 500 kV Phu Lam substation.
500 kV Đa Phước - Đầm Sen | 2x22 | 2031-2035 | New construction and connection of 500 kV Da Phuoc substation; consider separate busbar operation of 220 kV Ba Queo substation to limit short-circuit current
LNG Hiệp Phước giai đoạn 2 - Bình Chánh | 2x13 | 2031-2035 | Synchronize LNG Hiep Phuoc Phase II
Hóc Môn 2 - Rẽ cầu Bông - Bình Chánh 1 | 4x1 | 2031-2035 | New construction
500 kV TP Thủ Đức - Rẽ Công nghệ cao - Quận 9 | 4x5 | 2031-2035 | New construction
Nâng khả năng tải ĐD 220 kV Cát Lái - Thủ Đức | 2x13 | 2031-2035 | Upgrade to increase load capacity, synchronize with 500 kV Thu Duc City Substation
500 kV TP Thủ Đức - Cát Lái chuyển đấu nối đi trạm 220 kV Thủ Đức (tách liên kết Cát Lái - Thủ Đức) | 2x5 | 2031-2035 | New construction, connection to 500 kV Thu Duc City substation, change connection to limit short circuit current; select cross-section with suitable load capacity for 220 kV Cat Lai - Thu Duc transmission line (after renovation)
500 kV Bình Dương 2 đấu nối chuyển tiếp Bến Cát - Bến Cát 2 và Chơn Thành - Bến Cát 2 | 4x12 | 2031-2035 | New construction, connection to 220 kV side of 500 kV Binh Duong 2 substation
500 kV Bình Dương 2 - Rẽ Bến Cát - Tân Định 2 | 4x16 | 2031-2035 | New construction, connection to 220 kV side of 500 kV Binh Duong 2 substation
Bến Cát 3 - Rẽ Bến Cát 2 - Bình Dương 2 500 kV | 4x4 | 2031-2035 | New construction
Nâng khả năng tải ĐD 220 kV Uyên Hưng - Tân Định 500 kV | 2x16 | 2031-2035 | Upgrade to increase load capacity
Bàu Bàng đấu nối chuyển tiếp Chơn Thành - Bến Cát và Chơn Thành - 500 kV Bình Dương 2 | 4x1 | 2031-2035 | New construction, in case the 500 kV Binh Duong 2 substation is built later than the 220 kV Bau Bang substation, the name of the connection project will be "Bau Bang - Chon Thanh - Ben Cat and Chon Thanh - Ben Cat 2".
KCN Long Thành 2 - Rẽ Xuân Lộc - Long Thành | 4x1 | 2031-2035 | New construction
Cần Giuộc - Rẽ 500 kV Long An - Nam Hiệp Phước | 4x3 | 2031-2035 | New construction
500 kV Long An 2 - Rẽ Long An - Tân Phước | 4x10 | 2031-2035 | New construction
500 kV Tiền Giang - Rẽ Vĩnh Long - Sa Đéc | 4x15 | 2031-2035 | New construction
500 kV Tiền Giang - Rẽ Cai Lậy - Cao Lãnh | 4x4 | 2031-2035 | New construction
500 kV Bến Tre - Ba Tri | 2x16 | 2031-2035 | New construction, renewable energy release
500 kV Đồng Tháp - Rẽ Hồng Ngự - Lấp Vò | 4x12 | 2031-2035 | New construction and connection of 500 kV Dong Thap substation
500 kV An Giang - Rẽ Kiên Bình - Rạch Giá | 2x26 | 2031-2035 | New construction and connection of 500 kV An Giang substation
500 kV An Giang - Châu Thành (An Giang) | 4x28 | 2031-2035 | New construction and connection of 500 kV An Giang substation
500 kV An Giang - Rẽ Châu Đốc - Kiên Bình | 4x40 | 2031-2035 | New construction and connection of 500 kV An Giang substation
Vị Thanh - Rẽ Ô Môn - NĐ Cà Mau | 4x12 | 2031-2035 | New construction
Vĩnh Quang - Rẽ Rạch Giá - Kiên Bình | 2x1 | 2031-2035 | New construction
Bạc Liêu 4 - 500 kV Bạc Liêu (*) | 2x10 | 2031-2035 | New construction, synchronized with the scale and progress of regional power sources
Sóc Trăng - 500 kV Long Phú | 2x35 | 2031-2035 | New construction, renewable energy release
Nâng khả năng tải Sóc Trăng - Châu Thành (Hậu Giang) | 2x50 | 2031-2035 | Improve load capacity and release renewable energy
Nâng khả năng tải Bạc Liêu - Sóc Trăng | 2x42 | 2031-2035 | Improve load capacity and release renewable energy
Cà Mau 4 - Rẽ ĐG Cà Mau 1 - Cà Mau | 2x7 | 2031-2035 | New construction, synchronized with the scale and progress of regional power sources
Ước tính khối lượng đấu nối các nguồn NLTT | 500 | 2031-2035 | New construction, renewable energy release
Dự phòng phát sinh ĐZ 220 kV cải tạo và xây mới | 500 | 2031-2035 | Provision for load growth and power source development